## Sankarchand
Dc‡Rjv Kvh©vjq mg~‡ni AbyKz‡j Abybœqb ev‡R‡Ui †givgZ I msiÿb Lv‡Zi Ab¨vb¨ feb I ¯’vcbv DcLv‡Zi AvIZvq †givgZ Kv‡Ri AMÖMwZi cÖwZ‡e`b
| †Rjvt PzqvWv½v¦ |  |  | Dc‡Rjvt PzqvWv½v m`i¦ |  | For the Month of : |  | April'2019
µwgK bs | Aby‡gvw`Z ¯‹x‡gi bvg | Aby‡gvw`Z cÖv°wjZ g~j¨ | Pyw³ g~j¨ | wVKv`v‡ii bvg | Pzw³ m¤úv`‡bi ZvwiL | Pzw³ Abyhvqx KvR ïiæi ZvwiL | Pzw³ Abyhvqx KvR mgvwßi ZvwiL |  |  | gšÍe¨
[8 empty] | cwi‡‡kvwaZ A‡_©i cwigvb | ‡fŠZ AMÖMwZ(%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | ksKiP›`ª BDwbqb cwil` feb †givgZ I iÿbv‡eÿb | 12,00,000/- | 11,99,002.68 | ‡gmvm© gv`vbx G›Uvi cÖvBR,‡KvU †ivW,PzqvWv½v¦ | 2018-03-27 | 2018-04-05 | 2018-06-14 | 11,97,000/- | 100%
| wnmve iÿK |  | Dc-mnKvix cÖ‡KŠkjx |  |  |  |  | Dc‡Rjv cÖ‡KŠkjx
| GjwRBwW |  | GjwRBwW |  |  |  |  | GjwRBwW
| PzqvWv½v m`i,PzqvWv½v¦ |  | PzqvWv½v m`i,PzqvWv½v¦ |  |  |  |  | PzqvWv½v m`i,PzqvWv½v¦

## UNION-1
BDwbqb cwil` Kg‡cø· feb wbg©vb cÖKí (2q ch©vq) Gi AvIZvq wbg©vb Kv‡Ri AMÖMwZi cÖwZ‡e`b
‡Rjvt PyqvWv½v |  |  |  | Dc‡Rjvt PzqvWv½v m`i¦ |  |  |  | For the Month of: |  | April'2019
µwgK bs | Aby‡gvw`Z ¯‹x‡gi bvg | Aby‡gvw`Z cÖv°wjZ g~j¨ | Pyw³ g~j¨ | wVKv`v‡ii bvg | Pzw³ m¤úv`‡bi ZvwiL | Pzw³ Abyhvqx KvR ïiæi ZvwiL | Pzw³ Abyhvqx KvR mgvwßi ZvwiL | cwi‡kvwaZ A‡_©i cwigvb | ‡fŠZ AMÖMwZ(%) | gšÍe¨
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12
1 | †bnvjcyi BDwbqb cwil` Kg‡cø· feb wbg©vb cÖKí¦ | 1,28,52,658/- | 1,22,10,025/10 | †gmvm© cvifxb †UªWwm©, PzqvWv½v ¦ | 06.01.19 | 13.01.19 | 09.10.19 | - | 50%
| wnmve iÿK | [6 empty] | Dc‡Rjv cÖ‡KŠkjx
| GjwRBwW | [6 empty] | GjwRBwW
| PzqvWv½v m`i,PzqvWv½v¦ | [6 empty] | PzqvWv½v m`i,PzqvWv½v¦

## Flood
PHYSICAL AND FINICIAL MONTHLY PROGRESS REPORT
FLOOD & DISASTER DAMAGED RURAL ROAD INFRASTRUCTURE REHABILITATION PROJECT
LOCAL GOVERNMENT ENGINEERING DEPARTMENT
[13 empty] | For the Month of : |  | April'2019
Upazila : Sadar, District: Chuadanga.
Sl.No | ID Number | Name of Scheme | Road |  |  | Name of Contructor | Gross Estimate Cost (Tk.) | Salvage Amount (Tk) | Contruct Value (Tk) | Date of work order issued | Date of Commencement | Date of Completion | Physiceal Progress % | Expenditure Month | Amount Spent upto date (Tk) | Remarks
|  |  | Stating Change (m) | Ending Chinage (m) | Length (Km)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | 211733 | Rehabilitation of Dingdah Shankarchandra UP-Makaldanga-Doster hat -Kotali- Darsana hat Road from ch.9200m-10090m,10400m-12050m & Ch.13752m-18150m Package No.FDR/CHU/17-18/UNR/W 02 | 9200 10400 13752 | 10090 12050 18150 | 890 1650 4398 | M/S Jakaulla & Brothers, Jibannagar Chuadanga. | 14062973 | 0 | 23646401 | 20.09.18 | 20.1018 | 08.08.19 | 85%
|  | Accountant |  |  |  | Sub-Asstt. Engineer | [5 empty] | Upazila Engineer
|  | LGED |  |  |  | LGED | [5 empty] | LGED
|  | Chuadanga Sadar, Chuadanga. |  |  |  | Sadar, Chuadanga. | [5 empty] | Sadar, Chuadanga.

## VRRP
MÖvg moK cybevm©b cÖKí (VRRP)
| Name of Upazila: Chuadanga Sadar. | [6 empty] | Forth Month of : | April'2019
Conntract Code No | Name of work | Name of Contractor | Length/No | Estimated Cost | Contract Amount | Date of Contract Singing | Date of Commencement | Date of Completion | Prograss% | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
e-Tender/LGED/ Chua/ VRRP/18-19/W-01 | (PART-A) Rehabilitation of Boalmari-Amirpur road, ch. 00-800m (Road ID No-218235009) Part-B, Rehabilitation of Makaldanga-Dinnathpur road, Ch. 00-1175m (Road ID-21235027 (Part-C, Rehabilitation of Zebney Bhultia Road, Ch. 1115-1830m (Road ID-218235072) under Chuadanga Sadar, Chuadanga. | M/S. M. Rahman & Associates, Alamdanga, Chuadanga. | 0.800m, 1175m, 715m | - | 7399118.7 | - | - | - | 0%
(Package No-e-Tender/LGED/Chua/VRRRP/2018-19/W-02 | Rehabilitation of Yukta village manir house-Joyrampur railway station (Sadar Portion) road, at ch. 00-1090m, (B) Rehbilitation of Chuadanga R&H road-Taltala Ghat road, Ch. 00-1500m under Chuadanga Sadar, Chuadanga. (Package No-e-Tender/LGED/Chua/VRRRP/2018-19/W-02 | M/S. Nahar Enterprise, Alamdanga, Chuadanga. | 1090m,1500m | 7722918 | 7336772.1 | 1919-03-27 | 1919-04-02 | 1919-07-01 | 100%
Accountant |  |  | Sub-Asstt. Engineer |  |  |  | Upazila Engineer
LGED |  |  | LGED |  |  |  | LGED
Sadar, Chuadanga. |  |  | Sadar, Chuadanga. |  |  |  | Sadar, Chuadanga.

## PEDP-3
Third Primary Education Development Program (PEDP-3)
Local Government Engineering Department
Datail Contract Progress Report.
Upazila /Cost Center : Chuadanga(s) District- Chuadanga Region : Jessore.
[14 empty] | For the Month of: |  |  | April'2019
Package No | Name of Primary School | Estimated Cost | No of Tender Called | Date of IFT | Date of Tender Received | Date of Evaluation | Date of NOA Issuing | Contract Amount | Revised Contract Amount | Name of Contractor | Date of Contract | Date of Completion | Valid date of PG | Ext.Date of Completion | Phy.Prog. | Amount Spent (Const. Works) | Amount Spent (Soil. Test) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Adclrm
PEDPIII/CHD/SAD/2011-12/ W1.0229 | Ukto | 3388000 | 1st | 05.04.12 | 08.05.12 | 21.05.12 | 14.06.12 | 3725398.63 | 3725398.63 | M/S.Ranju Construction,Rail para, Chuadanga | 28.06.12 | 14.07.13 Actual 22.12.12 | 23.01.13 |  | 100 | 3568823 | 22000 | Final bill paid
| Boro Sholua | 3388000 | Coll |  |  |  |  | 3725398.62 | 3725398.62 | [5 empty] | 100 | 3655516 | 22000
Sub-Total Tk - |  | - | - | - | - | - | - | 7450797.25 | 7450797.25 |  | - | - | - | - | - | 7224339 | 44000
PEDPIII/CHD/SAD/2011-12/ W1.0644 | Hatikata | 2993000 | 1st | 05.04.12 | 08.05.12 | 21.05.12 | 13.06.12 | 3289339.37 | 3361339.37 | M/S.Ashabul Hoque Malik, Boro Bazar Chuadanga. | 28.06.12 | 11.07.13 Actual 20.12.12 | 23.01.13 |  | 100 | 3311381 | - | Final bill paid
| Kutubpur | 2993000 | Coll |  |  |  |  | 3289339.37 | 3361339.37 | [5 empty] | 100 | 3321163 | -
Sub-Total Tk - |  | 5986000 | - | - | - | - | - | 6578678.74 | 6722678.74 |  | - | - | - | - | - | 6632544 | -
PEDPIII/CHD/SAD/2011-12/ W2.1448 | Chandpur | 2385000 | 1st | 24-07-12 | 28.08.12 | 10.09.12 | 10.10.12 | 2571684.04 | 2571684.04 | M.S Asman construction Rail Bazar,Chuadanga | 05.11.12 | 11.11.13 | 28.02.14 | 22.01.14 | 100 | 2500911 |  | Final bill paid
Call
| Chhaighoria | 2385000 | [5 empty] | 2665158.89 | 2761158.89 | [5 empty] | 100 | 2708733
Sub-Total Tk - |  | 4770000 | - | - | - | - | - | 5236842.93 | 5332842.93 |  | - | - | - | - | - | 5209644 | -
PEDPIII/CHD/SAD/2011-12/ W1.0451 | Jadupur Community School | 5140000 | 1st | 05.04.12 | 08.05.12 | 21.05.12 | 14.06.12 | 5647807.29 | 5647807.29 | Md.Shiful Hasan Jr. Boro Bazar, Chuadanga | 28.06.12 | 14.10.13 Actual 22.12.12 | 23.01.13 |  | 100 | 5315348 | 21900 | Final bill paid
| Pirpur | 5140000 | Call |  |  |  |  | 5647807.28 | 5647807.28 | [5 empty] | 100 | 5576656 | 21900
Sub-Total Tk - |  | 10280000 | - | - | - | - | - | 11295614.57 | 11295614.57 |  | - | - | - | - | - | 10892004 | 43800
e-Tender/PEDP- III/CHD/SAD/2015-16/W2.3914 | Mortuzapur RNGPS | 6428900 | 1st | 31.12.15 | 27.01.16 | 07.02.16 | 18.02.16 | 5062646.23 | 5062646.23 | M/S. R.M Bricks,Collage para,chuadanga | 01.03.16 | 15.12.16 Actual 06.12.16 | 03.01.17 |  | 100 | 5060739 | 73000 | Final bill paid
Coll
e-Tender/PEDP- III/CHD/SAD/2015-16/W2.3915 | Sinduria | 2636000 | 1st | 31.12.15 | 27.01.16 | 07.02.16 | 18.02.16 | 2184528.36 | 2184528.36 | M/S.Ashabul Hoque Malik, Boro Bazar Chuadanga. | 01.03.16 | 15.12.16 Actual 03.12.16 | 31.12.16 |  | 100 | 2183240 |  | Final bill paid
Call
e-Tender/PEDP- III/ CHD/ SAD/ 2015-16/ W2.5775 | Baro Sholua RNGPS | 3742702 | !st Coll | 19.01.16 | 18.02.16 | 02.03.16 | 13.03.16 | 2867834.71 | 2867834.71 | M/S.R.M Bricks,Collage para, Chuadanga | 16.03.16 | 31.12.16 Actual 07.12.16 | 04.01.17 |  | 100 | 2867155 | 37000 | Final bill paid
e-Tender/ PEDP/ III /CHD/ SAD/2014-15/ W3.0611 | Kalupol | 399092 | 1st Call | 13.04.15 | 07.05.15 | 21.05.15 | 07.06.15 | 2428586.65 | 2428586.65 | M/S. Asman Construction | 16.06.15 | 30.03.16 Actual 29.03.16 | 30.04.16 |  | 100 | 2428164 |  | Final Bill Paid
| Kutubpur | 410331 | [12 empty] | 100
| Vanderdah | 329519 | [12 empty] | 100
| Garabaria | 363359 | [12 empty] | 100
| Kathuli | 406734 | [12 empty] | 100
| Belgachi | 317193 | [12 empty] | 100
| M.A Bari | 352965 | [12 empty] | 100
| Master para | 300363 | [12 empty] | 100
| Gaidghat | 407692 | [12 empty] | 100
| Sorisadanga | 426191 | [12 empty] | 100
| Accountant |  |  |  |  | Sub-Asstt.Engineer | [5 empty] | Upazilla . Engineer
| LGED | LGED |  |  |  | LGED | [5 empty] | LGED | LGED
| Chuadanga Sadar, Chuadanga. |  |  |  |  | Chuadanga Sadar,Chuadanga. | [5 empty] | Chuadanga Sadar, Chuadanga.
Sub-Total = | - | 3713439 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2428164 | -
e-Tender/ PEDP-III/CHD/SAD/2015-16/W2.0777 | Bhimrulla | 530936 | 1st Call | 23.02.16 | 21.03.16 | 23.03.16 | 07.04.16 | 358275.31 | 358275.31 | M/S. Asman Conatruction | 19.04.16 | 29.07.16 Actual 22.06.16 | 29.08.16 |  | 100 | 357794 |  | Final Bill paid
PEDP-III/CHD/ SAD/2011-12/ W3.0112 | Dosta | 194071 | 1st Call | 11.06.12 | 11.07.12 | 24.07.12 | 26.07.12 | 490024.02 | 490024.02 | Md. Omor Ali | 06.08.12 | 19.02.13 Actual 01.10.12 | 19.11.12 |  | 100 | 490000 |  | Final Bill paid
| Harishpur RNGPS | 282343 | [12 empty] | 100
| Rail Bazar | 243457 | [12 empty] | 100
Sub-Total = | - | 719871 | - | - | - | - | - | - | - | - | - | - | - | - | - | 490000
PEDPIII/CHD/SAD/2016-17/ W3.1288 | Jhajri | 363676 | 1st Call | 07.11.16 | 07.12.16 | 15.12.16 | 15.01.17 | 1710338.79 | 1710338.79 | M/S. Asman Conatruction | 25.01.17 | 31.05.17 | - | - | 100 | 1709027 |  | Final Bill paid
| Chandpur | 469948 | [12 empty] | 100
| Jhinuk Viddypit | 549000 | [12 empty] | 100
| Chaighoria | 332000 | [12 empty] | 100
Done for APP
Sub-Total Tk | - | 1714624 | - | - | - | - | - | - | - | - | - | - | - | - | - | 1709027 | - | -
e-Tender/PEDP/ III / CHD/SAD/ 2012-13/W7.076 | Ext. & Renovation of Chuadanga Sadar UEO | 300000 | 2nd Call | 27.05.14 | 23.06.14 | 30.06.14 | 20.07.14 | 206790.69 | 206790.69 | Md. Azijur Rahman.Jintola para,Chuadanga | 27.07.14 | 15.02.15 Actual 01.11.14 | 01.12.14 |  | 100 | 206000 |  | Final Bill paid
e-Tender/PEDP/ III / CHD/SAD/ 2016-17/ W18.0300 | Maintenance of Chuadanga Sadar URC Bhaban. | 200000 | 1st Call | 28.02.17 | 07.03.17 | 07.03.17 | 08.03.17 | 199453.5 | 199453.5 | M/S. Nur Samin Traders,Chuadanga | 09.03.17 | 11.04.17 |  |  | 100 | 199453 |  | Final Bill paid
e-Tender/PEDP/ III / CHD/SAD/ 2016-17/ G2.0296 | Furniture Supply of Chuadanga Sadar URC Bhaban. | 131088 | 1st Call | 28.02.17 | 07.03.17 | 07.03.17 | 08.03.17 | 130844 | 130844 | Md.Waliu; Islam Joarder | 09.03.17 | 11.04.17 |  |  | 100 | 130800 |  | Final Bill paid
e-Tender/PEDP/ III / CHD/SAD/ 2016-17/ W17.142 | Const.of Boundary Wall & Main Gate of Aliarpur | 1700275 | 1st Call | 01.06.17 | 07.07.17 | 11.07.17 | 23.07.17 | 3945875.51 | 3945875.51 | Madini Enterprise | 17.08.17 | 23.12.17 | Valid date Upto |  | 100% | 3231374 |  | Final Bill paid
| Boro Suluya Uttar para | 928834 | [12 empty] | 100%
| Dostha | 1700275 | [12 empty] | 100%
| Grishnagar | 1620745 | [12 empty] | 100%
Sub-Total Tk |  | 5950129 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
e-Tender/PEDP/ III / CHD/SAD/ 2017-18/ W3.1898 | Major Maint. of Srikole GPS | 500000 | 1st Call | 08.02.18 | 06.03.18 | 19.03.18 | 03.04.18 | 1249828.73 | 1249828.73 | M/S. Asman Construction, Rail Para Chuadanga | 19.04.18 | 24.06.18 | Valid date Upto |  | 100% | 1249559
| Major Maint. of Taltola GPS | 750000 | 1st Call | 08.02.18 | 06.03.18
e-Tender/PEDP/ III /CHD/ SAD/ 2017-18/ W3.1899 | Major Maint. of PitombobpurGPS | 450000 | 1st Call | 08.02.18 | 06.03.18 | 19.03.18 | 03.04.18 | 808867.87 | 808867.87 | Md. Boktiar Uddin, Nilmonigonj, Chuadanga. | 19.04.18 | 24.06.18 | Valid date Upto |  | 100% | 808241
| Major Maint. of Goborgara GPS | 360000 | 1st Call | 08.02.18 | 06.03.18
Sub-Total Tk | - | 810000 | - | - | - | - | - | - | - | - | - | - | - | - | - | -
e-Tender/PEDP/ III /CHD/ SAD/ 2017-18/ W17.802 | Const. work of Boundary wall & Gate of Boro Shoula GPS | 821301 | 1st Call | 28.01.18 | 26.02.18 | 05.03.18 | 20.03.18 | 3448718.59 | 3448718.59 | M/S. Asman Construction | 03.04.18 | 14.06.18 | Valid date Upto |  | 100% | 3448718.59
| Goherpur GPS | 1608759 | 1st Call | 28.01.18 | 26.02.18
| Nurnagar Jafarpur GPS | 1027707 | 1st Call | 28.01.18 | 26.02.18
Sub-Total Tk | - | 3457767 | - | - | - |  | - | - | - | - | - | - | - | - |  | - | -
e-Tender/PEDP/ III /CHD/ SAD/ 2017-18/ W17.803 | Const. work of Boundary wall & Gate of Subdia GPS | 2134419 | 1st Coll | 28.01.18 | 26.02.18 | 05.03.18 | 20.03.18 | 4390329.82 | 4390329.82 | M/S. Saiful Hasan Joarder | 03.04.18 | 14.06.18 | Valid date Upto |  | 100% | 4040819
| Taltola GPS | 2265318 | [5 empty] | 68415356.31 | 68655356.31
161800
[17 empty] | 58369614 | 197800
Accountant | [6 empty] | Sub-Asstt.Engineer |  |  |  |  | Upazila Engineer
LGED | [5 empty] | LGED | [5 empty] | LGED
Chuadanga Sadar, Chuadanga. | [5 empty] | Chuadanga Sadar, Chuadanga. | [5 empty] | Chuadanga Sadar, Chuadanga.
Note on K19: User:

## GKRIDP
Greater Kushtia District Rural Infrasture Development Project (GKRIDP)
Monthly Progress Report (Physical & Financial)
District- Chuadanga
[12 empty] | Month of: | April'2019
Sl. No | Upazila & Road ID No | Package No | Name of Scheme with location (Chainage) | Quantity |  | Estimated Cost (Tk) |  |  | Name of Contractor | Date of Contract | Contract Amount (TK) | Physical Progress | Date of Completion | Remarks
|  |  |  | Road (km) | Str.(m) | Road | Str. | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Chuadanga Sadar-218235001 | GKRIDP/01/CW-01 | Improvement of Pirpur-Gonger Ghat road at Ch. 00-2150m & Const. of 4 Nos. U-Drain (625mmx600mm), at Ch. 240m, 530m, 900m & 1810m on same road under Sadar, Chuadanga. | 2.15 | 4 | 15188588 | 478418 | 15667006 | Gonesh Pada Datta, Sher-e Bangla Sarok, Jhenaidah. | - | 14883655.7 | 10% | - | -
2 | Chuadanga Sadar-218235153 | GKRIDP/01/CW-02 | Improvement of Mohammod Jumm Shomser Ali House-Salmat Bazar via Alom Doctor road at Ch. 00-776m & Const. of 1 No. U-Drain (625mmx 600mm), at Ch. 510m under Sadar, Chuadanga. | 0.776 | 1 | 0 | 0 | 0 | M/S . Sit Bitan, Sher-e Bangla Sarok, Jhenaidah. | - | 595555 | 0% | - | -
3 | Chuadanga Sadar | GKRIDP/01/CM-01 | Periodic Maintenance of Hatikata R&H-Rajapur road from Ch. 00-1500m under Chuadanga Sadar, Chuadanga. | 1.5 | - |  | - |  | M/S. Emi Motors Chuadanga. | - | 1586109.55 | 10% | - | -
4 | Chuadanga Sadar | GKRIDP/01/CM-02 | Periodic Maintenance of Nilmonigonj-Digrir More road from Ch. 00-1500m under Chuadanga Sadar, Chuadanga. | 1.5 | - | - | - |  | Shohag Enterprise, Gobindopur, Alamdanga, Chuadanga. | - | 4479596.75 | 20% | - | -
5 | Chuadanga Sadar | GKRIDP/01/CM-03 | Periodic Maintenance of Pirpur Bottola H/O. Kashem Mondul-H/O. Shajahan road from Ch. 00-890m under Chuadanga Sadar, Chuadanga. | 0.89 | - | - | - |  | M/S. Chamok Enterprise Baniakndor, Jhenaidah. | - | 23,15,454.950 | 20% | - | -
6 | Chuadanga Sadar | GKRIDP/01/CM-04 | Periodic Maintenance of Chhotosalua to Grishnagar Bazar road from Ch. 00-2000m under Chuadanga Sadar, Chuadanga. | 2 | - | - | - |  | M/S. Habibur Rahman, Mirpur Bazar, Mirpur, Kushtia. | - | 69,34,960.100 | 15% | -
| Accountant |  |  |  | Sub-Asstt. Engineer | [5 empty] | Upazilla . Engineer
| LGED |  |  |  | LGED | [5 empty] | LGED
| Chuadanga Sadar, Chuadanga. |  |  |  | Chuadanga Sadar, Chuadanga. | [5 empty] | Chuadanga Sadar, Chuadanga.

## Muktizoddha
f~wgnxb I Am”Qj gyw³‡hv×v‡`i evm ¯’vb cÖK‡íi
gvwmK AMÖMwZi cÖwZ‡e`b t
| Dc‡Rjvt PzqvWv½v m`i¦ ‡Rjvt PzqvWv½v¦ |  |  |  | For the Month of: |  | April'2019
µwgK bs | ¯‹x‡gi bvg | cÖv°wjZ e¨q/eivÏ (UvKvq) | wVKv`vi/wVKv`vix cÖwZôv‡bi bvg | Pzw³ g~j¨ (UvKvq) | Kvh©v‡`k cÖ`v‡bi ZvwiL | Kvh©v‡`k Abyhvqx KvR mgvwßi ZvwiL | Kv‡Ri †fŠZ AMÖMwZ (%) | gšÍe¨
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
01) | 2012-2013 A_© erm‡ii f~wgnxb I Am”Qj gyw³‡hv×v‡`i Rb¨ evm¯’vb wbg©vb cÖK‡íi AvIZvq PzqvWv½v ‡Rjvi PzqvWv½v m`i Dc‡Rjvi
| 1) ‡gvt dRjyi ingvb wcZv- †gv: Mvwik gÛj, mvs- Puv`cyi | 9,18,439/- | †gmvm© gv`vbx G›UvicÖvBR ‡KvU© †ivW,PzqvWv½v¦ | 43,63,350/- | 23.09.2013 | 20.10.2014 | 100%
| 2) †gvt nvweeyi ingvb wcZv-g„Zt‡Lvi‡k` Avjx mvsÑ†mL cvov | 9,18,439/-
| 3) †gvt Avqye Avjx wcZv-g„Zt Avãyj Kv‡`i mvs- h`ycyi | 9,18,439/-
| 4) †gvt Avãyj Rwjj wcZv-Avg` Avjx gÛj mvs-h`ycyi | 9,18,439/-
| 5) †gvt Kvjy †mL wcZv- Avdmvi Avjx †mL mvs- evMvbcvov Gi evox wbg©vb ¦ | 9,18,439/-
45,92,195
2014-15 A_© ermit
| 1) Elvivbx miKvi,¯^vgx- g„Z Awbj Kzgvi miKvi,Mªvg- †evqvwjqv,KzZecyi BDwc¦ | 8,84,656/- | ‡gvt mvgmy‡Ïvnv gwjøK nKcvov, PzqvWv½v | 22,54,767/86 | 10.03.2015 | 10.10.2015 | 100%
| 2) †gvt kIKZ Avjx,wcZv- g„Z gywÝ †m‡K›`vi Avjx,MÖvg-‰kjgvix, †eMgcyi BDwc | 8,84,656/-
| 3) †gvQvt wiwRqv LvZzb, ¯^vgx-g„Z gyw³‡hv×v AvjvDwÏb wek¦vm,MÖvg- nvRivnvUx,Pzqvt ‡cŠimfv, PzqvWv½v | 8,84,656/-
26.53.968/-
| Accountant |  | Sub-Asstt. Engineer |  |  | Upazilla . Engineer
| LGED |  | LGED |  |  | LGED
| Chuadanga Sadar, Chuadanga. |  | Chuadanga Sadar, Chuadanga. |  |  | Chuadanga Sadar, Chuadanga.
f~wgnxb I Am”Qj gyw³‡hv×v‡`i evm ¯’vb wbg©vb cÖK‡íi
gvwmK AMÖMwZi cÖwZ‡e`b t
| Dc‡Rjvt PzqvWv½v m`i¦ ‡Rjvt PzqvWv½v¦ |  |  |  |  | For the Month of: |  | April'2019
µwgK bs | ¯‹x‡gi bvg | cÖv°wjZ e¨q/eivÏ (UvKvq) | wVKv`vi/wVKv`vix cÖwZôv‡bi bvg | Pzw³ g~j¨ (UvKvq) | Kvh©v‡`k cÖ`v‡bi ZvwiL | Kvh©v‡`k Abyhvqx KvR mgvwßi ZvwiL | Kv‡Ri †fŠZ AMÖMwZ (%) | gšÍe¨
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
01) | f~wgnxb I Am”Qj gyw³‡hv×v‡`i Rb¨ evm¯’vb wbg©vb cÖK‡íi AvIZvq PzqvWv½v ‡Rjvi PzqvWv½v m`i Dc‡Rjvi f~wgnxb I Am”Qj gyw³‡hv×v‡`I wbwg©Z evm¯’v‡b 5wU Mevw` cïi †mW I 5wU †cvwëª †mW wbg©vb¦ | 4,09,930.15 | †gvt eLwZqvi DÏxb, bxjgwbMÄ,PzqvWv½v¦ | 3,68,937.13 | 21.03.18 | 12.06.2018 | 100%
1) ‡gvt dRjyi ingvb
2) †gvt nvweeyi ingvb
3) †gvt Avqye Avjx
4) †gvt Avãyj Rwjj
5) †gvt Kvjy †mL¦
| Accountant |  | Sub-Asstt. Engineer |  |  | Upazilla . Engineer
| LGED |  | LGED |  |  | LGED
| Chuadanga Sadar, Chuadanga. |  | Chuadanga Sadar, Chuadanga. |  |  | Chuadanga Sadar, Chuadanga.

## GKP
Local Government Engineering Department.
GKP-Project
Schemes-wise implementation Progress Repart
| Upazila : Chuadanga Sadar. |  |  |  |  | For the Month of : |  |  | April'2019
Conntract Code No | Name of work | Name of Contractor | Length/No | Estimated Cost | Contract Amount | Date of Contract Singing | Date of Commencement | Date of Completion | Prograss% | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
GKP/01/CH/W-01 | Development of road from Sarabaria Bazar-Mohammadpur via Sujayetpur –Batikadanga road at Ch.oom-950m.. | M/S. Abdullah –Al-Mamun Sharabaria Jibannagar,Chuadanga | 950 | 4300000 | 4085000 | 09.12.12 | 09.12.2012 | 05.10.2013 | 100%
GKP/01/CH/W-02 | Development of road from Hizolgari GC-Kotali-Begompur UP road at Ch.6100m-6295m. | Md. Ohidul Islam Jor.,Rail para Chuadanga | 195 | 1095920 | 1041200 | 09.12.12 | 09.02.2012 | 07.06.2013 | 100% |  |  | 1
GKP/01/CH/W-03 | Development of road from Begompur – Zadupur road at Ch.1543m-2502m | M/s.Munshi Enterprise ,Boro Bazar Chuadanga | 959 | 4300000 | 4085000 | 09.12.12 | 09.12.2012 | 05.10.2013 | 100%
GKP/01/CH/W-04 | Development of road from Voltia – Tirbila road at Ch.3600m-4380m ii) Const.of 375mmx450mm 4nos U-drain on same road at ch.13m,90m,270m & 460m. | M/S.Asabul Hoque Malik,Boro Bazar Chuadanga | 780 | 4295462 | 4081200 | 15.04.13 | 15.04.13 | 10.01.2014 | 100%
GKP/01/CH/W-27 | Development of road from Dingadah-Makaldanga-Doster hat road at Ch.7750m-9200m.. | M.N Enterprise. ,Arampara Chuadanga | 1450 | 8100000 | 7695950 | 09.05.13 | 06.06.2013 | 03.04.2014 | 100%
GKP/01/CH/W-34 | Development of Venderdah- Chaiwghoria road ( from Chaiwghoria Kachukhali Kamar Dokan-Puraton Venderdah road) at Ch.00m-600m. | M/S Konika Enterprise,40 Bagha Jotin road,Jhenaidah | 600 | 3587308 | 3408600 | 09.05.13 | 06.06.2013 | 03.04.2014 | 100%
GKP/01/CH/W-18 | Development of roadfrom Pirpur Bottola-Gonjer Hat para road at Ch.00m-890m & Const. of 1 Nos 625mx600m U-drain at Ch.400m on same road. | M/S Ranju Construction,Cenama hallpara Chuadanga | 890 | 4287215 | 4163850 | 09.05.13 | 06.06.2013 | 03.04.2014 | 100%
GKP/01/CH/W-35 | Development of road from Gaidthghat Robiul house-up to Dinnathpur Samasuddins house road at Ch.00m-612m & . Const. of 3 Nos 625mx 600m U-drain at Ch.284m,434m & 464m on same road. | M/S. Lipi Jewlers Boro Bazar,Chuadanga | 612 | 3615336 | 3682200 | 09.05.13 | 06.06.2013 | 03.04.2014 | 100%
GKP/01/CH/W-15 | Development of road from Shomvo Nagar-Shaheb Nagar road at Ch.00m-910m | Md. Kamal Hosain,Jehala Munshigonj Alamdanga | 910 | 4318603 | 4103050 | 21.05.13 | 17.06.2013 | 14.03.2014 | 100%
GKP/01/CH/W-16 | Development of road from Subdia R&H - Baliakandi road at Ch.00m-820m | Md.Rezaul Karim,Alifuddin road Alamdanga Chuadanga | 820 | 4299179 | 4085000 | 21.05.13 | 17.06.2013 | 14.03.2014 | 100%
GKP/01/CH/W-17 | Development of road from Nilmonigonj – Kulchara More road at Ch.2700m-3485m.. | Md. Shiful Kabir Yousuf ,Dosomi Damurhuda.Chua. | 785 | 4289824 | 4084050 | 21.05.13 | 17.06.2013 | 14.03.2014 | 100%
GKP/01/CH/W-19 | Development of road from Goraitupi Bazar- Sabdalpur via Teghoria Southpara road at Ch.00m-900m.. | Md. Shamshudwoha Mollic, Hoque para, Chuadanga | 900 | 4278278 | 4077400 | 21.05.13 | 17.06.2013 | 14.03.2014 | 100%
GKP/02/CH -41 | Development of Alukdia Bazar under Alukdia UP | Md. Shamshudwoha Mollic Hoque para, Chuadanga | - | 2363253 | 2245800 | 20.10.13 | 20.10.2013 | 18.04.14 | 100% |  |  | 2
GKP/02/CH/-51 | Development of road from Begumpur Doster hat-Kotali road at Ch.700 m -1200m & Ch.5644m-5950m | Md. Ali Nur Kibria, Gulshanpara Chuadanga | 806 | 3995070 | 3796200 | 22.10.13 | 06.11.2013 | 04.07.2014 | 100%
GKP/02/CH/-52 | Development of road from Begumpur Doster hat-Kotali road at Ch.00-1750m & Const.of 05 Nos 625mx600m on same U-drain at Ch.128m,356m, 670m,1020m & 1355m road. | M/S. Lipi Jewlers,Mukti para, Chuadanga | 1750 | 6785501 | 6833350 | 22.10.13 | 06.11.2013 | 04.07.2014 | 100%
GKP/02/CH/-50 | Improvement of road from Choto Solua-Grishnagar Bazar road at Ch.1000-1391m & 1806m-2026m & Const.of 01 No 625mx600m on same U-drain at Ch.1230m, | M/S Razu Construction, Zintola para, Chuadanga | 391 | 2631704 | 2596350 | 22.10.13 | 2013-06-11 | 2014-04-07 | 100%
GKP/02/CH/-49 | Improvement of road from Sankarchandra-Boldia Madrasa road at Ch.3250-4330m & Const. of 01 No 126mx 625mx 600m on same U-drain. | Md. Azad Ali Taltola,Chuadanga | 1080 | 4512460 | 4393750 | 22.10.13 | 2013-06-11 | 04/07/214 | 100%
GKP/02/CH-69 | Development of road from Joyrampur -Chuadanga road at Ch.1730 m -3730m & Const. of 01 No 625mx 600m U-drain at ch. 26000 m on same road . | M/S. Shahidul Enterprise. ,Gulshan para Chuadanga | 2000 | 8016528 | 7709250 | 22.12.13 | 01.01.2013 | 28.08.14 | 100%
GKP/02/ | Improvement of Nilmoni gong-Culchaara road at ch.3485m-4075m Under Sadar Upazila. | M/S.Sirishti International, Malopara Chuadanga | 590 | 2763929 | 2264735.95 | 29.04.14 | 13.09.14 | 15.05.15 | 100%
CH/-89
GKP/02/ | Improvement of Bultia R & H Tiorbila road at ch. 370m-1310m Under Sadar Upazila. | M/S. R.M Bricks | 940 | 4296913 | 3394797.06 | 22.04.14 | 13.09.14 | 15.05.15 | 100%
CH/-90 |  | Collage para Chuadanga
GKP/02/ | Improvement of Makal danga – Shreekol road at ch.00m-970m . | M/S. R.M Bricks Collage para Chuadanga | 970 | 4285590 | 3459583.28 | 22.04.14 | 13.09.14 | 15.05.15 | 100%
CH/-91
GKP/02/CH/-93 | Improvement of Nilmoni gong-Digrir more road at Ch.1500-2310 m &Const. of 01 No 625mx 600m U-drain.at ch.19720m on same road . | RFM Construction,Puraton para Chuadanga | 810 | 4105939 | 3407932.44 | 21.04.14 | 13.09.14 | 15.05.15 | 100%
GKP/02/CH-94 | Development of road from Gauid ghat Rail Station Uzirjpur Tallu Sjpring Mills road (Sadar Portion) at Ch.00m -1028m at Sadar, Chuadanga. | M/S. Shaharin Hoque Malik. ,Rail para Chuadanga | 1028 | 4188223 | 3429834.4 | 21.04.14 | 13.09.14 | 15.05.15 | 100%
GKP/02/CH-81 | Improvement of Begumpur –Jodupur via Bill Para road at ch.375m-1435m . | M/S.Asman Construction,Rail para Chuadanga | 1060 | 4188844 | 3394464.18 | 14.05.14 | 17.10.14 | 15.05.15 | 100%
GKP/02/CH/-92 | Improvement of Dingadah –Makaldanga–Dosterhat road at Ch.3803m-4748 m & Const. of 02 No 625mx600m size U-drain Culvert at ch.4400m & 4700m on same road . | M/S.Asman Construction,Rail para Chuadanga | 945 | 5337118 | 4369505.48 | 14.05.14 | 17.10.14 | 15.05.15 | 100% |  |  | 3
GKP/02//CH-70 | Improvement of i)Bihari Railghat–Gaidghat foot boll field road at Ch.00-400 m ii) Improvement of Ismail house at Gaid ghat Shokat house at Gaidghat Ch.00-230m iii) Const. of 625mmx 600mm size U-drain Culvert on Bihari Rail ghat–Gaidghat footboll field road at ch. 100m-225m. | M/S.Madani Enterprise ,Court road Chuadanga | 630 | 3149428 | 3133304.45 | 22.12.13 |  | 28.08.14 | 100%
GKP/02/ CH/-97 | Improvement of i)Gaidghat Rail Station-Uzirpur Tallu Spining Mill road at Ch.1028 -2000 m ii) Const .of 600mm x625mm U-Type drain culvert at ch.1750m on the same road | M/S.Madani Enterprise,Court road Chuadanga | 972 | 4264575 | 3408674.5 | 24.11.14 | 10.12.14 | 09.04.14 | 100%
GKP/04 | Improvement of road on Jibne - Vultia road at ch.00-1115m Under Sadar Upazila. | M/S. Prema Construction | 1115 | 4699255 | 3418712.92 | 01.12.15 | 01.01.16 | 27.09.16 | 100%
CH/-128 |  | Muktipara Chuadanga
GKP/04/ | Improvement of road Boalia -Makaldanga road at ch.00-890m road Sadar Upazila | M/S. Prema Construction | 890 | 4293960 | 3087485.78 | 01.12.15 | 01.01.16 | 27.09.16 | 100%
CH/-130 |  | Muktipara Chuadanga
GKP/04/CH/-131 | Improvement of road Padmabila UP ( Khajura )- Dhuturhate road at ch.3770-5375m & Const. of 04 No U-Drain culvert ( 625mmx 600mm ).at ch.4120m,4949m,5026 & 5065m on same road | M/S. R.M Bricks Collage para Chuadanga | 1605 | 8974052 | 6505987.4 | 01.12.15 | 01.01.16 | 27.09.16 | 100%
GKP/04/CH/-132 | Improvement of road Jalsuka - Chayghoria School road at ch.3120-3870m. | M/S.Madani Enterprise ,Court road Chuadanga | 750 | 3185071 | 2398674.25 | 01.12.15 | 01.01.16 | 27.09.16 | 100%
GKP/04/CH/-133 | Improvement of road 4 Mile R&H - Kalibhanderdah via Basu Bhanderdah road at ch.2510-3510m road under, Sadar Upazila | M/S. R.M Bricks Collage para Chuadanga | 1000 | 427805 | 3118701.2 | 01.12.15 | 01.01.16 | 27.09.16 | 100%
GKP/04/CH/129 | Improvement of road of Makaldanga-Dinnathpur road at ch.1115m-1916m . | Md. Shaharin Haque Malik Chuadanga. | 801 | 4208590 | 3434581.95 | 06.12.13 | - | - | 100%
GKP/04/CH/139 | Improvement of road of Hatikata R & H Rajapur road at ch.1500m-2305m Under Sadar Upazila. Const.of 2 Nos U-Type Drain at Ch.1877m-2184m on same road | Md. Shaharin Haque Malik Chuadanga. | 805 | 5635968 | 3881487.32 | 11.04.16 | 17.04.16 | 17.01.17 | 100%
GKP/04/CH/140 | Improvement of road Jodupur-Begumpur road at ch.00-1027m .Const. of 01 No U-Type Drain .at ch.337m on same road | M/S. Ashabul Haque Malik Boro Bazar Para Chuadanga | 1027 | 5759968 | 4120691.34 | 28.03.16 | 04.04.16 | 09.01.17 | 100%
GKP/04/CH/142 | Improvement of road Tengramari -Culchra road at ch.1310-2278m road Sadar Upazila | Md. Shaharin Haque Malik Chuadanga. | 968 | 5758368 | 3973278.05 | 11.04.16 | 17.04.16 | 17.01.17 | 100% |  | 4
GKP/04/CH/-143 | Improvement of road Nuton Bhanderdah-Bhanderdah road at ch.00-1046m. | M/S.Shahana Construction Cenima Hall para, Chuadanga | 1046 | 5757232 | 4141167.58 | 28.03.16 | 04.04.16 | 05.02.17 | 100%
GKP/04/CH/-144 | Improvement of road Sankarchandra-Chighoria at ch.00-985m& Const.of 1 Nos U-Type Drain at Ch.507m on same road . | M/S. Ashabul Haque Malik Boro Bazar Para Chuadanga | 985 | 5757824 | 4078128.87 | 28.03.16 | 04.04.16 | 09.01.17 | 100%
GKP/04/CH/-141 | Improvement of Zal Shuka Bridge to Srikole road at ch.428-1207m & Const.of 1 Nos U-Type Drain at Ch.432m on same road . | Md.Shaharin Haque Malik Jhenaidah Bus Stand Para Chuadanga | 779 | 4598444 | 3172930 | 11.04.16 | 17.04.16 | 17.01.17 | 100%
GKP/05/CH/-160 | Improvement of Mohammadzuma-Mortuzapur road at ch.576-1700 m &2374-3238m Const.of 3 Nos U- Drain at Ch.988m,1350m and 1482 on same road . | M/S. R.M Bricks Collage para Chuadanga | 1988 | 11281019 | 11263963.16 | 7.0217 | 13.02.17 | 11.02.18 | 100%
GKP/05/CH/-165 | Improvement of Begumpur-Jodupur via Bilpara road at ch.1435m1997 m & 2230m-2741m under Sadar Upazila . | M/S.Asman Construction,Rail para Chuadanga |  | 5694001 | 5682619.856 | 13.02.17 | 19.02.17 | 19.12.17 | 100%
GKP/05/CH/-179 | (A)Improvement of Begumpur-Jodupur road BC at ch.2502-3160m(B) Const.of 1 No PVC Pipe Culvert a t Ch.3130 on same road . | M/S Madani Enterprise Court road ,Chuadanga | 658 | 3561027 | 3204924 | 6.07.17 | 02.08.17 | 28.05.18 | 100%
GKP/05/CH/-181 | (A)Improvement of Choto Salua -Grishnagar Bazar road by BC at ch.2026m-2842m &(B)Const.of two Nose PVC Pipe Culvert at Ch.3133m,2745m.. | M/S Khandaker Shahin Ahmed.Goalchamot,Faridpur. | 816 |  | 4298645 | 10.08.17 | 17.08.17 | 12.04.18 | 100%
GKP/05/CH/-182 | Improvement of Batikadanga Sujayetpur road at ch.950m-1368m | M/S Madani Enterprise Court road ,Chuadanga | 418 | 2301800 | 2071620 | 26.07.17 | 02.08.17 | 28.05.18 | 100%
GKP/05/CH/-180 | (a)Improvement of Kalupole bazar-Gostobehar GCCR road at ch.43m-1305m(B) Const.of two Nose PVC Pipe Culvert at Ch.1129m,1290m.. | Md Jahirul Islam Mollikpara Meherpur. | 1262 | 7515000 | 6763500 | 12.07.17 | 19.07.2017 | 04.05.2018 | 100%
GKP/05/CH/-192 | (a)Improvement of Makaldanga-Dinnathpur road by BC at ch.1915-3050m (B) Const.of four Nose U-Type drain at Ch.1950m,2242m,2275m & 2447m on same road . | M.S Shila Construction,Bhultia Bodorjong Bazar, Chuadanga. | 1135 | 8079451 | 7675478.45 |  |  |  | 100%
GKP/05/CH/-193 | (a)Improvement of Jalsuka Bridge-Sree Kole road at ch.1207m-1332m. | Md Abu Zafur Montu Gulshan para, Chuadanga. |  | 14394417 | 792592.6 | 11.06.18 | 17.06.18 | 14.03.19 | 100%
GKP/05/CH/-194 | (a)Improvement of Mohammad Jumma-Mortuzapur road by BC at ch.1700-2374m & 3238m-3450m (B) Const.of One No U-Type drain at Ch.1793m on same road . | M.S. R.M Bricks Collage para, Chuadanga. | 886 | 6168349 | 5859931.5 | 11.06.18 | 17.06.18 | 14.03.19 | 100% |  | 5
GKP/05/CH/-196 | (a)Improvement of Begumpur-Jodupur Via Bill para road by BC at ch.00-370m & 2741m-2873 m (B) Const.of One No U-Type drain at Ch.370m on same road . | R.F.M Construction Puratan para, Chuadanga. | 502 | 3223896 | 3062701.2 | 07.06.18 | 13.06.18 | 10.03.19 | 100%
GKP/05/CH/-195 | (a)Improvement of Begumpur-Dosterhat Via Kotali road by BC at ch.00-730m (B) Const.of Two Nos U-Type drain at Ch.373m & 580m on same road . | Md. Moula Biswas, Darsana,Chuadanga | 750 | 7403363 | 4468194.85 | 24.06.18 | 30.06.18 | 27.03.19 | 100%
GKP/05/CH/-205 | (a)Improvement of Alukdia R&H-Jhoragdata road by BC at ch.00-895m (B) Const.of 2 Nos U-drain at Ch.200m & 769m on same road b).Improvedment of Begumpur-Zadupur road bt BC Ch.00-1543m (b)Const.of 2 Nos U-drain at Ch.1030m & 1450m on same road | M/S Taru Miru Construction, Collage Para, Chuadanga | 2438 | 14394417 | 13671846.15 | 07.08.18 | 13.08.18 | 12.08.19 | 80%
Accountant |  | Sub-Asstt. Engineer |  |  |  | Upazila Engineer
LGED |  | LGED |  |  |  | LGED
Chuadanga Sadar, Chuadanga. |  | Chuadanga Sadar, Chuadanga. |  |  |  | Chuadanga Sadar, Chuadanga.
|  |  | Local Government Engineering Department. | [8 empty] | 5
GKP-Project
Schemes-wise implementation Progress Repart
Fund Demand
Conntract Code No | Name of work | Name of Contractor | Length/No | Estimated Cost | Contract Amount | Date of Contract Singing | Date of Commencement | Date of Completion | Prograss%
Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
GKP/05/CH/-165 | Improvement of Begumpur-Jodupur via Bilpara road at ch.1435m1997 m & 2230m-2741m under Sadar Upazila . | M/S.Asman Construction,Rail para Chuadanga |  | 5694001 | 5682619.856 | 13.02.17 | 19.02.17 | 19.12.17 | 70% | 30
GKP/05/CH/-181 | (A)Improvement of Choto Salua -Grishnagar Bazar road by BC at ch.2026m-2842m &(B)Const.of two Nose PVC Pipe Culvert at Ch.3133m,2745m.. | M/S Khandaker Shahin Ahmed.Goalchamot,Faridpur. | 816 |  | 4298645 | 10.08.17 | 17.08.17 | 12.04.18 | 70% | 32
GKP/05/CH/-182 | Improvement of Batikadanga Sujayetpur road at ch.950m-1368m | M/S Madani Enterprise Court road ,Chuadanga | 418 | 2301800 | 2071620 | 26.07.17 | 02.08.17 | 28.05.18 | 20% | 15
GKP/05/CH/-180 | (a)Improvement of Kalupole bazar-Gostobehar GCCR road at ch.43m-1305m(B) Const.of two Nose PVC Pipe Culvert at Ch.1129m,1290m.. | Md Jahirul Islam Mollikpara Meherpur. | 1262 | 7515000 | 6763500 | 12.07.17 | 19.07.2017 | 04.05.2018 | 70% | 45.89
122.89
Upazila Engineer
LGED
Chuadanga Sadar, Chuadanga.

## GOBM
PHYSICAL AND FINICIAL MONTHLY PROGRESS REPORT
RURAL ROAD AND CULVERT MAINTENANCE PROGRAMME
LOCAL GOVERNMENT ENGINEERING DEPARTMENT
FY: 2018-2019 | [12 empty] | For the Month of : |  | April'2019
Upazila : Sadar, District: Chuadanga.
Sl.No | ID Number | Name of Scheme | Road |  |  | Name of Contructor | Gross Estimate Cost (Tk.) | Salvage Amount (Tk) | Contruct Value (Tk) | Date of work order issued | Date of Commencement | Date of Completion | Physiceal Progress % | Expenditure Month | Amount Spent upto date (Tk) | Remarks | 1
|  |  | Stating Change (m) | Ending Chinage (m) | Length (Km)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | 228585 | Mainenance of Shamvunagar-Shabebnagor Road from ch.00-910m Package No.e-Tender/Chua/GOBM /18-19/W-20 | 0 | 910 | 910 | M/S Emi Motors Daulatdiar Sardarpara Chuadanga. | 1883665 | 0 | 1789481.75 | 24.10.18 |  |  | 100%
2 | 228584 | Mainenance of Grisnagar Bazar-Begumpur UP road from ch.258-680m .Package No e-Tender .LGED/CHUA/GOBM/18-19/W-18 | 258 | 680 | 422 | Titu Enterprise Damurhuda,Chuadanga | 1208845 | 0 | 1148402.75 | 24.10.18 | 13.11.18 | 12.01.19 | 100%
3 | 230701 | Mainenance of Nimtala G.K. maincanal road from ch.00-1970m .Package No e-Tender .LGED/CHUA/GOBM/18-19/W-49 | 0 | 1970 | 1970 | Md.Mortuza Kadargonj para Chuadanga | 4544506 | 0 | 4317280.7 | 01.11.18 | 20.11.18 | 19.01.19 | 100%
4 | 230760 | Mainenance of Alukdia UP-Pirpur Ferryghat-Damurhuda GC(Sadar Portion) road from ch.00-2100m .Package No e-Tender .LGED/CHUA/GOBM/18-19/W-38 | 0 | 2100 | 2100 | M/S R.M Bricks Collagepara Chuadanga | 6897262 | 0 | 6552398.9 | 01.11.18 | 25.11.18 | 08.02.19 | 100%
5 | 230761 | Mainenance of Badorganj R&H-Andulbaria G.C(Sadar Portion) road from ch.5540-8250m .Package No e-Tender .LGED/CHUA/GOBM/18-19/W-39 | 5540 | 8250 | 2710 | M/S Nowshad Enterprise ,V.J School road Chuadanga | 19801163 | 0 | 18811104.85 | 10.12.18 | 29.12.18 | 28.04.19 | 100%
6 | 230757 | Pariodic Mainenance of Dingadah G.C-Darsona(Sadar Portion) road from ch.600-5000m .Package No e-Tender .LGED/CHUA/GOBM/18-19/W-36 | 600 | 5000 | 4400 | Titu Enterprise Damurhuda, Chuadanga | 13339795 | 0 | 12672805.25 | 10.12.18 | 09.01.19 | 09.05.19 | 100%
7 | 230756 | Pariodic Mainenance of Grishnagar bazar-Andulbaria GC road from ch.00-2310m .Package No e-Tender .LGED/CHUA/GOBM/18-19/W-35 | 0 | 23100 | 2310 | M/S Raju Construction,Mollick Para ,Chuadanga | 6839401 | 0 | 6497430.95 | 11.11.18 |  |  | 100%
|  | Accountant |  |  |  |  | Sub-Asstt. Engineer | [5 empty] | Upazila Engineer
|  | LGED |  |  |  |  | LGED | [5 empty] | LGED
|  | Sadar, Chuadanga. |  |  |  |  | Sadar, Chuadanga. | [5 empty] | Sadar, Chuadanga.
5

## IRIDP-2
Important Rural Infrastructure Development Project (IRIDP-2)
Monthly Progress Report (Physical & Financial)
District- Chuadanga
[10 empty] | For the Month of : |  | April'2019
Sl. No | Upazila & ID No | Package No | Name of Scheme with location (Chainage) | Quantity |  | Estimated Cost (Tk) |  |  | Name of Contractor | Date of Contract | Contract Amount (TK) | Physical Progress | Date of Completion | Remarks
|  |  |  | Road (km) | Str.(m) | Road | Str. | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | 33994 | IRIDP-2/ CH U/DW-06 | Improvement of 6 mile R&H road - Shahapur Primary School via Burapara village road at ch.00-1000m | 1 |  | 5839645 |  | 5839645 | M/S Prema Constion, Muktipara, chuadanga | 03.12.15 | 4233747.42 | 100% | 08.06.2016
2 | 33995 | IRIDP-2/ CH U/DW-07 | Improvement of Joyrampur - Chuadanga road at ch.1275-1890m & Cont. of 2 nos 0.625mx0.60m culvert on same road at ch. 1525m & 1890m | 0.615 | 1.25 | 2065709 | 194541 | 2260250 | M/S Madani Enterprise,Coart road, chuadanga | 23.12.15 | 1617929.9 | 100% | 07.04.2016
3 | 34004 | IRIDP-2/ CH U/DW-17 | Improvement of Goherpur GCCR - Baztikadanga road at ch.00-680m | 0.68 | - | 3638832 |  | 3638832 | Md. Shaharin Haque Malik, Chuadanga | 06.12.15 | 3619824.17 | 100% | 08.06.2016
4 | 46196 | IRIDP-2/CHU/ DW-18 | Improvement of Badargong R&H-Ashanadapur Bazar via Kutubpur Bazar road at ch.4170-7100m Const.of 07 Nos 0.625mx0.600m culvert at Ch.4607m,5135m,6378m, 6676m,6841m & 6950m on the same road | 2.93 |  | 16384633 |  | 16384633 | Md. Shaharin Haque Malik, Chuadanga | 11.04.16 | 11469243 | 100% | 17.04.2017
5 | 34015 35071 | IRIDP-2/CHU/ DW-34 | Improvement of a) Bhultia-Kharagoda road at ch.1660-2341m b) Bhultia Eidgah-Nobinagor (Purathun Eidgah-Gorosthan) road at Ch.00m-347m). | 1.028 |  | 6977789 |  | 6977789 | M/S. R.M. Bricks Collage para, Chuadanga. | 13.10.16 | 6960288.939 | 100% | 19.05.2017
6 | 74794 | IRIDP-2/CHU/ DW-42 | Improvement of Garabaria-Basatipara Mosjid Mour-Makaldanga Bazar road at ch.00-830m) & (b) Const. of 01 (One) nos 0.625mx0.600m culvert at ch. 460m on same road. | 0.83 |  | 4520596 | 86644 | 4607240 | Md. Shaharin Haque Malik, Chuadanga | 15.01.17 | 3079936.06 | 100% | 19.09.2017
7 | 74795 | IRIDP-2/CHU/ DW-43 | Improvement of (a) Sankarchandra-Boldia Madrasha road at ch.00m-1500m & (b) Const. of 03 (Three) nos 0.625mx0.600m culvert at ch. 18m,135m &700m on same road. | 1.5 |  | 7282136 | 259932 | 7542068 | Md. Shaharin Haque Malik, Chuadanga | 15.01.17 | 5015477.92 | 100% | 19.09.2017
8 | 74793 | IRIDP-2/CHU/ DW-41 | Improvement of (a) Dingadah (Sankarchandra U.P)-Makaldanga-Doster hat -Kotali-Darsana hat road at ch.5220m-6820m & (b) Const. of 05 (Five) nos 0.625mx0.600m culvert at ch. 15955m,6120m, 6435m,6495 & 6670m on same road. | 1.6 |  | 8307338 | 433221 | 8740559 | M/S. Asman Construction ,Rail para,Chuadanga. | 17.01.17 | 5876289.66 | 100% | 21.09.2017
9 | 92973 | IRIDP-2/ CHU/DW-48 | Mantenance of (a) Bodargonj R & H Ashanandapur Via Kutubpur road at ch.00m-3100m road. | 3100 |  | 3577750 |  | 3577750 | Toma Construction & Co.Limited,Kakrail Ramna,Dhaka. | 20.06.17 | 3219975.83 | 100% | 26.04.2018
10 | 92974 | IRIDP-2/ CHU/DW-49 | Mantenance of Bohalgachi-Choyghoria road at ch.00m-2500m road. | 2500 |  | 3668053 |  | 3668053 | Toma Construction Ramna,Dhaka. | 20.06.17 | 3301247.79 | 100% | 26.04.2018
11 | 92975 | IRIDP-2/ CHU/DW-50 | Mantenance of Belgachi -Jaforpur road at ch.00m-1270m road. | 1270 |  | 2760252 |  | 2760252 | Toma Construction Ramna,Dhaka. | 20.06.17 | 2484227.49 | 100% | 26.04.2018
12 | 112328 | IRIDP-2/ CHU/DW-55 | (A)Improvement ofChandpur-Sarabaria GCCR road at ch.00m-1515m (b) Const. of 04 nos 0.625mx0.600m culvert at ch. 331m,674m, 905m & 1044m on same road. | 1515 |  | 8540203 | 316628 | 8856832 | Mozahar Enterprise Khanjahan Ali Road Khulna. | 12.11.17 | 7971149.09 | 100% | 18.08.2018
13 | 112330 | IRIDP-2/ CHU/DW-56 | (A)Improvement of Doster Hat-Uzzalpur road at ch.00m-800m (b) Const. of 01 nos 0.625mx0.600m culvert at ch. 371m on same road. | 800 |  | 5423166 | 79157 | 5502323 | Mozahar Enterprise Khanjahan Ali Road Khulna. | 12.11.17 | 4952091.68 | 100% | 18.08.2018
14 | 112331 | IRIDP-2/ CHU/DW-57 | (A)Improvement of Kotali Bazar-Furshesdpur road at ch.00m-955m road(b) Const. of 03 nos 0.625mx0.600m culvert at ch. 210m,294m& 388m on same road. | 955 |  | 5023397 | 237471 | 5260869 | Mozahar Enterprise Khanjahan Ali Road Khulna. | 12.11.17 | 4734782.1 | 100% | 18.08.2018
15 | 112332 | IRIDP-2/ CHU/DW-58 | (A)Improvement of Boalia Sirajs house-Battola bazar road at ch.00m-1052m road(b) Const. of 01 nos 0.625mx0.600m culvert at ch.395m on same road. | 1052 |  | 5959214 | 79157 | 6038371 | Mozahar Enterprise Khanjahan Ali Road Khulna. | 12.11.17 | 5434534.55 | 100% | 18.08.2018
16 | 112340 | IRIDP-2/ CHU/DW-66 | (A)Improvement of Khashpara Bagdia GCCR via Pokamari road at ch.00m-500m(b) Const. of 01 nos 0.625mx0.600m culvert at ch.264m on same road. | 500 |  | 2580379 | 79157 | 2659536 | Jahirul Limited Mollikpara,Meherpur | 24.1017 | 2393583.18 | 100% | 30.07.18
17 | 145798 | IRIDP-2/ CHU/DW-73 | Improvement of Boaila R&H Boalia FWC road at ch.00m-584m | 584 |  | 3359624 |  | 3359624 | Mozahar Enterprise Khulna. | 19.02.18 | 3023661.68 | 100% | 23.11.18
18 | 145796 | IRIDP-2/ CHU/DW-71 | Improvement of Zadobpur R&H-Sultan House road at ch.00m-1000m | 1000 |  | 5914402 |  | 5914402 | Mozahar Enterprise Khulna. | 19.02.18 | 5322961.92 | 100% | 23.11.18
19 | 145797 | IRIDP-2/ CHU/DW-72 | Improvement of Bhultia Eidgah-Nabinagar road at ch.1782m-2650m | 868 |  | 5264910 |  | 5264910 | Mozahar Enterprise Khulna. | 19.02.18 | 4738419.25 | 100% | 23.11.18
20 | 2098810 | IRIDP-2/ CHU/DW-80 | (a)Improvement of Tagiri Madrasha-Kolagach Primary School road at ch.00m-1350m(b) Const. of 04 nos culvert at ch. 117m,490m, 1170m & 1308m onthe same road. | 1350 |  | 8125586 | 335016 | 8460602 | R.F.M Construction Puratun Para,Chuadanga. |  | 8037571.9 | 60%
21 | 209882 | IRIDP-2/ CHU/DW-81 | (a)Improvement of Titudah-Kamribeel road at ch.00m-1000m(b) Const. of 02 nos culvert at ch. 640m & 880m on the same road. | 1000 |  | 5891194 | 167508 | 6058702 | Zoarder Enterprise Mirpur,Kushtia. |  | 5755766.9 | 100%
22 | 231829 | IRIDP-2/ CHU/DW-83 | (a)Improvement of Bara Salua GCCR-Kalupole road at ch.00m-1200m(b) Const. of 02 nos culvert at ch. 400m & 787m on the same road. | 1200 |  | 8490312 | 189625 | 8679937 | Md.Nuruzzaman Goni | 22.11.18 | 8245940.15 | 100%
23 | 231830 | IRIDP-2/ CHU/DW-84 | (a)Improvement of Tagori More-Tagori Schol road at ch.00m-600m(b) Const. of 01 nos culvert at ch. 330m on the same road. | 600 |  | 4034560 | 94813 | 4129373 | M/S Emi Motors Daulatdiar Chuadanga. | 25.11.18 | 3922904.35 | 100%
| Accountant |  |  |  |  | Sub-Asstt. Engineer |  |  |  |  | Sub-Asstt. Engineer
| LGED |  |  |  |  | LGED |  |  |  |  | LGED
| Chuadanga Sadar, Chuadanga. |  |  |  |  | Chuadanga Sadar, Chuadanga. |  |  |  |  | Chuadanga Sadar, Chuadanga.
Important Rural Infrastructure Development Project (IRIDP-2)
Monthly Progress Report (Physical & Financial)
[5 empty] | District- Chuadanga |  |  |  | NO PRINT
Fund Demand.
Sl. No | Upazila & ID No | Package No | Name of Scheme with location (Chainage) | Quantity |  | Estimated Cost (Tk) |  |  | Name of Contractor | Date of Contract | Contiact Amount (TK) | Physical Progress | Date of Completion | Remarks
|  |  |  | Road (km) | Str.(m) | Road | Str. | Total
1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | 112328 | IRIDP-2/ CHU/DW-55 | (A)Improvement ofChandpur-Sarabaria GCCR road at ch.00m-1515m (b) Const. of 04 nos 0.625mx0.600m culvert at ch. 331m,674m, 905m & 1044m on same road. | 1515 |  | 8540203 | 316628 | 8856832 | Mozahar Enterprise Khanjahan Ali Road Khulna. | 12.11.17 | 7971149.09 | 35% | 18.08.2018 | 56
2 | 145798 | IRIDP-2/ CHU/DW-73 | Improvement of Boaila R&H Boalia FWC road at ch.00m-584m | 584 |  | 3359624 |  | 3359624 | Mozahar Enterprise Khulna. | 19.02.18 | 3023661.68 | 15% | 23.11.18 | 24
3 | 145796 | IRIDP-2/ CHU/DW-71 | Improvement of Zadobpur R&H-Sultan House road at ch.00m-1000m | 1000 |  | 5914402 |  | 5914402 | Mozahar Enterprise Khulna. | 19.02.18 | 5322961.92 | 15% | 23.11.18 | 37
4 | 145797 | IRIDP-2/ CHU/DW-72 | Improvement of Bhultia Eidgah-Nabinagar road at ch.1782m-2650m | 868 |  | 5264910 |  | 5264910 | Mozahar Enterprise Khulna. | 19.02.18 | 4738419.25 | 15% | 23.11.18 | 33
150
Upazilla . Engineer
LGED
Chuadanga Sadar, Chuadanga.

## KDRIDP
Khulna Division Rural Infrastructure Development Project (KDRIDP)
Monthly Progress Report (Physical & Financial)
District- Chuadanga
[11 empty] | For the Month of: |  | April'2019
Sl. No | Upazila & ID No | Package No | Name of Scheme with location (Chainage) | Quantity |  | Estimated Cost (Tk) |  |  | Name of Contractor | Date of Contract | Contract Amount (TK) | Physical Progress | Date of Completion | Remarks
|  |  |  | Road (km) | Str.(m) | Road | Str. | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Chuadanga Sadar 98097 | KDRIDP/CHUA/W-01/ 2016-17 | (A) Improvement of Jalshuka -Chaygharia School road by BC at ch.00-2000m (B) Const. of Three Nos U-Type Drain Culvert at ch.28,750 & 1782m on same road . | 2000 |  | 11536359 | 273713 | 11810072 | M/S Saiful Hassan Joarder,Boro Bazar,Chuadanga | 04.06.17 | 11808890.428 | 100% | 07.04.18
2 | 98099 | KDRIDP/CHUA/W-02/ 2016-17 | (A) Improvement of Akandobaria Azizuler house -Gunon Para Hudar bari l road by BC at ch.00-1500m (B) Const. of Two Nos U-Type Drain Culvert at ch.400& 770m on same road. | 1500 |  | 8284108 | 198504 | 8482612 | Md. Bokthar Uddin, Nilmonigonj,Chuadanga. | 06.06.17 | 8458418.91 | 80% | 09.04.18
3 | 100832 | KDRIDP/CHUA/W-08/ 2016-17 | (A) Improvement of Bhultia R & H-Tiorbila road by BC Ch.1310-2332m (B) Const. of One No U- Drain Culvert at ch.2140m on same road. | 1022 |  | 5676477 | 108645 | 5785122 | Md. Ali Reza,Ferighat Road,Chuadanga. | 13.06.17 | 5206609.8 | 100% | 17.03.18
4 | 110280 | KDRIDP/CHUA/W-15/ 2016-17 | (A) Improvement of Sankarchandra -Boldia Madrasha road by BC at ch.1500-3000m (B) Const. of Two Nos U- Drain Culvert at ch.1824m & 2140m on same road. | 1500 |  | 8247334 | 234351 | 8481685 | Mohammed Eunus & Brother(Pvt)Ltd P.S:Panchlaish,Chittagong. | 13.09.17 | 7633516.5 | 100% | 19.06.18
5 | 110282 | KDRIDP/CHUA/W-16/ 2016-17 | (A) Improvement of Shambunagar-Shahebnagar road by BC at ch.910-2410m (B) Const. of 2 Nos U-Drain Culvert at ch.1390 & 2250m on same road. | 1500 |  | 8823488 | 236046 | 9059534 | Mohammed Eunus & Brother(Pvt)Ltd P.S:Panchlaish,Chittagong | 13.09.17 | 8153580.6 | 100% | 19.06.18
6 | 100830 | KDRIDP/CHUA/W-06/ 2016-17 | (A) Improvement of Batikadanga-Sujayetpur road by BC at ch.1368-2000m (B) Const. of 2 Nos U-Drain Culvert at ch.1398 &1603 m on same road. | 632 |  | 3719457 | 208168 | 3927625 | M/S. R.M. Bricks, Collage para,Chuadanga | 03.07.17 | 3534862.5 | 100% | 06.04.2018
7 | 100831 | KDRIDP/CHUA/W-07/ 2016-17 | (A) Improvement of Sankarchandra-Boldia adrasha road by BC at ch.3000-3395m (B) Const. of 1 No U-Drain Culvert at ch.3100 m on same road. | 395 |  | 2682938 | 104084 | 2787022 | M/S. Shahana Construction, Cenama Hall para,Chuadanga | 03.07.17 | 2508319.8 | 100% | 06.04.2018
8 | 110279 | KDRIDP/CHUA/W-14/ 2016-17 | (A) Improvement of Jalshuka -Chaygharia School road by BC at ch.2000-3215m (B) Const. of 03 Nos U-Type Drain Culvert at ch.2328,2555 & 2812m on same road | 1215 |  | 7252549 | 354069 | 1881928 | Mohammed Eunus & Brother(Pvt)Ltd P.S:Panchlaish,Chittagong. | 13.09.17 | 6845956.2 | 100% | 19.06.18
9 | 100829 | KDRIDP/CHUA/W-05/ 2016-17 | (A) Improvement of Dingadah Shankarchandra UP Makaldanga-Doster Hat road by BC at ch.6830-7735m (B) Const. of 01 Nos U-Type Drain Culvert at ch. 7165m on same. | 905 |  | 5220051 | 104084 | 5324135 | M/S Saiful Hasan Joarder,Bara Bazar,Chuadanga. | 09.07.17 | 4791721.5 | 100% | 11.04.18
10 | 143041 | KDRIDP/CHUA/M-07/ 2017-18 | Maintenance of Nilmoniganj-Kulchara more road at ch.00-2615m. | 2615 |  | 5216921 |  | 5216921 | Mozahar Enterprise, Khulan | 19.02.18 | 4695228.9 | 100% | 29.08.18
11 | 143042 | KDRIDP/CHUA/M-08/2017-18 | Maintenance of Chuadanga-Makaldanga road at ch.3800-5250m. | 1450 |  | 2699547 |  | 2699547 | Mozahar Enterprise, Khulna. | 19.02.18 | 2429592.3 | 100% | 29.08.18
12 | 143043 | KDRIDP/CHUA/M-09/ 2017-18 | Maintenance of Joyrampur- Chuadanga road at ch.3730-8000m. | 4270 |  | 7379240 |  | 7379240 | Mozahar Enterprise, Khulna. | 19.02.18 | 6641316 | 100% | 29.08.18
13 | 143044 | KDRIDP/CHUA/M-10/ 2017-18 | Maintenance of 5 Miles R & H Balshapur via Harukandi road at ch.00-4190m. | 4190 |  | 7277107 |  | 7277107 | Mozahar Enterprise Khulna. | 19.02.18 | 6549396.3 | 100% | 29.08.18
14 | 143045 | KDRIDP/CHUA/M-11/ 2017-18 | Maintenance of Titudah U.P-Golapnagar road at ch.00-1050m. | 1050 |  | 1644559 |  | 1644559 | Mozahar Enterprise Khulna. | 19.02.18 | 1480103.1 | 100% | 29.08.18
15 | 188973 | KDRIDP/CHUA/W-41/ 2017-18 | Part (A.1)Improvement of Dehi-Darsana road at (ch.1750-2138m.) Part-(A-2) Const of 1No U-Type drain Culvert at Ch.1969 on the same road Part-B (1)Improvement o Makaldanga-Srikele road (ch.970-3265m) Part-B (2) Const.of 4 Nos U-Type drain Culvert at Ch.1222,2274,2453 & 3115m on the same road. | 2683 |  | 16950188 | 533348 | 17483536 | Md.Babul Akter | 12.06.18 | 16609359.167 | 40% | 06.03.19
16 | 188963 | KDRIDP/CHUA/W-37/ 2017-18 | Part (A.1)Improvement of Subdia R&H-Baliakandi road at (ch.820-1265m.), Part(B-1)Improvement of Bhultia R&H Tiorbila road (ch.2332-3445m). | 1558 |  | 9645963 |  | 9645963 | M/S Padma Traders | 12.06.18 | 9163664.665 | 100% | 06.03.19
17 | 195627 | KDRIDP/CHUA/W-27/ 2017-18 | Part (A.)Improvement of Nutun Bhanderdah-Bashu Bhanderdah-Bhanderdah-Jugirhuda road at (ch.4575-6200m.), Part(B) Const of 2 Nos U-Type drain Culvert at Ch.4910m & 5225m on the same road road. | 1625 |  | 10736178 |  | 10736178 | M/S Nitu Traders | 04.07.18 | 10199369.1 | 70% | 08.04.19
18 | 188968 | KDRIDP/CHUA/W-38/ 2017-18 | Part (A.1)Improvement of Nehalpur GCCR-Krishnopur road at (ch.1000-1992m.)(A.2) Const of 4 Nos U-Type drain Culvert at Ch.11105m,1362m,1583m & 1940m on the same road (B.1) Improvement of Shambunagar -Shahebnagar road at ch.(2140m -3410m)(B.2) Const of 2 Nos U-Type drain Culvert at Ch.2503m & 2674m on the same road road . | 2262 | 669126 | 12325005 |  | 12325005 | Babul Mia | 22.05.18 | 12344424 | 100% | 06.04.19
19 | 191990 | KDRIDP/CHUA/W-39/ 2017-18 | Part (A.1)Improvement of Grisangar Bazar-Bagumpur U.P. road at (ch.00-25m, 70-258m)& Ch.680-1400m. (A-2) Const of 4 Nos U-Type drain Culvert at Ch.740m,775m,858m & 1173m on the same road (B.1) Improvement of Grisangar Bazar-Bagumpur U.P. road at ch.(1800m -5100m)(B.2) Const. of 1 No Box Culvert at ch.4806m (B-3)Const of 2 Nos U-Type drain Culvert at Ch.2396m & 3311m on the same road road . | 4233 |  | 27924476 | 1220776 | 291452.52 | Jahirul Limited Mollaik para Meherpur |  | 25641306.285 | 50%
20 | 218803 | KDRIDP/CHUA/W-40/ 2017-18 | Part (A.1)Improvement of Batikadanga-Sujayetpur road at (ch.2000-2858m) (A-2) Const of 3 Nos U- drain at Ch.2685m,2730m & 2815m on the same road (B.1) Improvement of Alukdia Shesd Member House-Rabbani Mondol Housevia Huchokpara road at ch.(00m-1780m (B.2) Const. of 4 drain at Ch.700m 1302m,1505m &1760m on the same road road . | 2638 |  | 17848713 | 868830 | 18717543 | Md.Anwar Hossain Alamdanga Chuadanga. | 17.10.18 | 16579655.55 | 40% | 20.07.19
21 | 237211 | KDRIDP/CHUA/W-23/ 2017-18 | Part (A.1)Maintenance Jafarpur - Hanurbaradi road at ch.00-2400 (Part-B) Maintenace of Joyrampur - Chuadanga road at ch.00-1850m ( Part-C ) Maintenance of Aloukdia UP- Kandmpur road at Ch.00-2200m. | 6450 |  | 15026935 |  | 15026935 | M/S Kaba Enterprise,Rail Para,Chuadanga. | 23.12.18 | 14275588.25 | 15% | 27.09.19
21 | 237211 | KDRIDP/CHUA/M-23/2017-18 | (Part -A)Maintenance of Jafarpur-Hanurbaradi road at Ch.00-2400m. (Part-B) Maintenance of Joyrampur-Chuadanga road at ch.00-1850m(Part-C)Maintenance of Alukdia UP-Khadimpur road at Ch.00-2200m | 6450 |  | 15026935 |  | 15026935 | M/S Kaba Enterprise,Rail Para,Chuadanga. | 23.12.18 | 14275588.25 | 0% | 27.09.19
Accountant |  |  |  |  | Sub-Asstt. Engineer |  |  |  |  | Upazila Engineer
LGED |  |  |  |  | LGED |  |  |  |  | LGED
Chuadanga Sadar, Chuadanga. |  |  |  |  | Chuadanga Sadar, Chuadanga. |  |  |  |  | Chuadanga Sadar, Chuadanga.
Khulna Division Rural Infrastructure Development Project (KDRIDP)
Monthly Progress Report (Physical & Financial)
District- Chuadanga
Fund Demand.
Sl. No | Upazila & ID No | Package No | Name of Scheme with location (Chainage) | Quantity |  | Estimated Cost (Tk) |  |  | Name of Contractor | Date of Contract | Contiact Amount (TK) | Physical Progress | Date of Completion | Remarks
|  |  |  | Road (km) | Str.(m) | Road | Str. | Total
1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Chuadanga Sadar 98097 | KDRIDP/CHUA/W-01/2016-17 | (A) Improvement of Jalshuka -Chaygharia School road by BC at ch.00-2000m (B) Const. of Three Nos U-Type Drain Culvert at ch.28,750 & 1782m on same road | 2000 |  | 11536359 | 273713 | 11810072 | M/S Saiful Hassan Joarder,Boro Bazar,Chuadanga | 04.06.17 | 11808890.428 | 70% | 07.04.18 | 51
3 | 100832 | KDRIDP/CHUA/W-08/2016-17 | (A) Improvement of Bhultia R & H-Tiorbila road by BC Ch.1310-2332m (B) Const. of One No U- Drain Culvert at ch.2140m on same road | 1022 |  | 5676477 | 108645 | 5785122 | Md. Ali Reza,Ferighat Road,Chuadanga. | 13.06.17 | 5206609.8 | 70% | 17.03.18 | 47.8
4 | 110280 | KDRIDP/CHUA/W-15/2016-17 | (A) Improvement of Sankarchandra -Boldia Madrasha road by BC at ch.1500-3000m (B) Const. of Two Nos U- Drain Culvert at ch.1824m & 2140m on same road | 1500 |  | 8247334 | 234351 | 8481685 | Mohammed Eunus & Brother(Pvt)Ltd P.S:Panchlaish,Chittagong. | 13.09.17 | 7633516.5 | 20% | 19.06.18 | 53
5 | 110282 | KDRIDP/CHUA/W-16/2016-17 | (A) Improvement of Shambunagar-Shahebnagar road by BC at ch.910-2410m (B) Const. of 2 Nos U-Drain Culvert at ch.1390 & 2250m on same road | 1500 |  | 8823488 | 236046 | 9059534 | Mohammed Eunus & Brother(Pvt)Ltd P.S:Panchlaish,Chittagong | 13.09.17 | 8153580.6 | 10% | 19.06.18 | 56
6 | 100830 | KDRIDP/CHUA/W-06/2016-17 | (A) Improvement of Batikadanga-Sujayetpur road by BC at ch.1368-2000m (B) Const. of 2 Nos U-Drain Culvert at ch.1398 &1603 m on same road | 632 |  | 3719457 | 208168 | 3927625 | M/S. R.M. Bricks, Collage para,Chuadanga | 03.07.17 | 3534862.5 | 20% | 06.04.2018 | 35
242.8
2
Sl. No | Upazila & ID No | Package No | Name of Scheme with location (Chainage) | Quantity |  | Estimated Cost (Tk) |  |  | Name of Contractor | Date of Contract | Contiact Amount (TK) | Physical Progress | Date of Completion | Remarks
|  |  |  | Road (km) | Str.(m) | Road | Str. | Total
1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
10 | 143041 | KDRIDP/CHUA/M-07/2017-18 | Maintenance of Nilmoniganj-Kulchara more road at ch.00-2615m | 2615 |  | 5216921 |  | 5216921 | Mozahar Enterprise, Khulan | 19.02.18 | 4695228.9 | 10% | 29.08.18 | 46
11 | 143042 | KDRIDP/CHUA/M-08/2017-18 | Maintenance of Chuadanga-Makaldanga road at ch.3800-5250m | 1450 |  | 2699547 |  | 2699547 | Mozahar Enterprise, Khulna. | 19.02.18 | 2429592.3 | 10% | 29.08.18 | 24
12 | 143043 | KDRIDP/CHUA/M-09/2017-18 | Maintenance of Joyrampur- Chuadanga road at ch.3730-8000m. | 4270 |  | 7379240 |  | 7379240 | Mozahar Enterprise, Khulna. | 19.02.18 | 6641316 | 10% | 29.08.18 | 66
13 | 143044 | KDRIDP/CHUA/M-10/2017-18 | Maintenance of 5 Miles R & H Balshapur via Harukandi road at ch.00-4190m. | 4190 |  | 7277107 |  | 7277107 | Mozahar Enterprise Khulna. | 19.02.18 | 6549396.3 | 10% | 29.08.18 | 65
14 | 143045 | KDRIDP/CHUA/M-11/2017-18 | Maintenance of Titudah U.P-Golapnagar road at ch.00-1050m. | 1050 |  | 1644559 |  | 1644559 | Mozahar Enterprise Khulna. | 19.02.18 | 1480103.1 | 10% | 29.08.18 | 14
457.8
Upazilla . Engineer
LGED
Chuadanga Sadar, Chuadanga.

## NBIDGPS
Local Government Engineering Department
Need Based Infrastructure Development of Govt. Primary School (1st phase) (NBIDGPS)
Details Contract Progress Report
| Upazila: Chuadanga Sadar. | [7 empty] | District: Chuadanga. | [7 empty] | For the Month of : |  | April'2019
Package No. | Name of Primary School | Estimated cost | Scheme Approved Date | APP Approved Date | Tender Publication (Date) | Tender Opening (Date) | Date Evalation | Contract Amount | Name of Contructor | Date of Contract | Date of Completion | Phy prog |  |  |  | Amount Spent (Const.work) | Fund Demend | Amount Spent (Soil) | Amount Spent (Topo) | Remarks
Tergeted UE
[12 empty] | Actual | April | May | June
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
e-Tender/ NBIDGPS/ CHD/SAD/2017-18 /W1.00166 | Const.of Gaidghat GPS | 7301797 | 07.12.17 | 01.01.18 | 16.01.18 | 13.02.18 | 26.02.18 | 6571617.3 | M.S Liton Traders | 26.04.18 | 31.01.19 | - | 85% |  |  | 2197202 |  | 27500 | 12000
e-Tender/ NBIDGPS/ CHD/SAD/2017-18/ W1.00168 | Const.of Alukdia GPS | 7301797 | 07.12.17 | 01.01.18 | 16.01.18 | 13.02.18 | 26.02.18 | 6571617.3 | M.S Liton Traders | 26.04.18 | 31.01.19 | - | 85% |  |  | 3802798 |  | 27500 | 12000
e-Tender/ NBIDGPS/ CHD/SAD/2017-18/ W1.00167 | Const.of AkandabariaGPS | 6622041 | 10.01.18 | 04.02.18 | 27.02.18 | 28.03.18 | 10.04.18 | 5959836.9 | Mozahar Enterprise (PVT) LTD. | 13.05.18 | 12.02.19 | - | 100% |  |  | 5131773 |  | 27500 | 12000
e-Tender/ NBIDGPS/ CHD/SAD/2017-18/ W1.00169 | Const.of 1 No Chuadanga GPS | 7509553 | 10.01.18 | 04.02.18 | 27.02.18 | 28.03.18 | 10.04.18 | 6758597.7 | Mozahar Enterprise (PVT) LTD. | 13.05.18 | 12.02.19 | - | 100% |  |  | 6168227 |  | 27500 | 12000
e-Tender/ NBIDGPS/ CHU/SAD/2017819/ W1.03159 | Const.of Teghori GPS | 9398089 | 12.11.18 | 22.11.18 | 10.12.18 | 03.01.19 | 16.01.19 | 8928184.55 | M/S Faiem Enterprise | 18.02.19 | 21.11.19 | - | 15% |  |  | - | - | - | -
e-Tender/ NBIDGPS/ CHU/SAD/2017-18/ W1.02927 | Const.of Boalmary GPS | 7851779 | 04.11.18 | 18.11.18 | 03.12.18 | 20.12.18 | 03.01.19 | 7459190.05 | Gonesh Pada Datta | 07.02.19 | 10.11.19 | - | 20% |  |  | - | - | - | -
[8 empty] | 42249043.8 | [7 empty] | 17300000 |  | 110000 | 48000
| Accountant |  |  |  |  | Sub-Asstt. Engineer | [9 empty] | Upazila Engineer
| Chuadanga Sadar |  |  |  |  | Chuadanga Sadar | [9 empty] | Chuadanga Sadar
| Chuadanga. |  |  |  |  | Chuadanga. | [9 empty] | Chuadanga.

## NBIDNNGPS
Local Government Engineering Department
Need Based Infrastructure Development of Newly Nationalized Govt. Primary School (1st phase) (NBIDNNGPS-1)
Details Contract Progress Report
District: Chuadanga.
| Upazila: Chuadanga Sadar. | [14 empty] | For the Month of: |  |  | April'2019
Package No. | Name of Primary School | Estimated cost | Scheme Approved Date | APP Approved Date | Tender Publication (Date) | Tender Opening (Date) | Date Evalation | Contract Amount | Name of Contructor | Date of Contract | Date of Completion | Phy Prog. |  |  |  | Amount Spent (Const.work) | Fund Demend | Amount Spent (Soil) | Amount Spent (Topo) | Remarks
Tergeted UE
[12 empty] | Actual | April | May | June
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
e-Tender/ NBIDNNGPS/CHD/ SAD/2017-18 /W1.00228 | Const.of Aria RNGPS | 6803252 | 31.12.17 | 04.02.18 | 19.02.18 | 14.03.18 | 27.03.18 | 6122926.8 | Mozahar Enterprise (PVT) LTD. | 03.05.18 | 08.05.19 |  | 95% |  |  | 5389840 |  | 27500 | 12000
e-Tender/ NBIDNNGPS/CHD/SAD/2017-18/ W1.00229 | Const.of Chandipur Malik Sharani RNGPS | 6676753 | 31.12.17 | 04.02.18 | 19.02.18 | 14.03.18 | 27.03.18 | 6009077.7 | Mozahar Enterprise (PVT) LTD. | 03.05.18 | 08.05.19 |  | 100% |  |  | 5162881 |  | 27500 | 12000
e-Tender/ NBIDNNGPS/CHD/SAD/2017-18/ W1.00230 | Const.of Nafarkandi RNGPS | 6547290 | 31.12.17 | 04.02.18 | 19.02.18 | 14.03.18 | 27.03.18 | 5892561 | Mozahar Enterprise (PVT) LTD. | 03.05.18 | 08.05.19 |  | 100% |  |  | 5021122 |  | 27500 | 12000
e-Tender/ NBIDNNGPS/CHD/SAD/2017-18/ W1.00231 | Const.of Police Line RNGPS | 7721076 | 31.12.17 | 04.02.18 | 19.02.18 | 14.03.18 | 27.03.18 | 6948968.4 | Mozahar Enterprise (PVT) LTD. | 03.05.18 | 08.05.19 |  | 100% |  |  | 4000000 |  | 27500 | 12000
e-Tender/ NBIDNNGPS/CHD/SAD/2017-18/ W1.00433 | Const.of Jibna RNGPS | 7301302 | 12.02.18 | 14.03.18 | 27.03.18 | 18.04.18 | 03.05.18 | 6936234.25 | Shohag Enterprise | 27.05.18 | 31.05.19 |  | 80% |  |  | 1923541 |  | 27500 | 12000
e-Tender/ NBIDNNGPS/CHD/SAD/2017-18/ W1.00902 | Const.of Motair Rahman Malik RNGPS | 6606865 | 01.04.18 | 17.04.18 | 26.04.18 | 16.05.18 | 21.05.18 | 6276521.75 | M/S. Proma Traders | 21.06.18 | 30.04.19 |  | 85% |  |  | 2453624 |  | 27500 | 12000
e-Tender/ NBIDNNGPS/CHU/CHU/2018-19/ W1.02622 | Const.of Class room. Mohammad Joma PS. | 8707923 | 01.11.18 | 12.11.18 | 27.11.18 | 13.12.18 | 23.12.18 | 8272526.85 | M/S K.N Enterprise | 28.01.19 | 31.10.19 | - | 15% |  |  | - | - | - | -
e-Tender/ NBIDNNGPS/CHU/CHU/2018-19/ W1.02623 | Const.of Class room. Sankarchandra Sonirvor PS. | 7980917 | 01.11.18 | 12.11.18 | 27.11.18 | 13.12.18 | 23.12.18 | 7581871.15 | Titu Enterprise | 28.01.19 | 31.10.19 | - | 20% |  |  | - | - | - | -
e-Tender/ NBIDNNGPS/CHU/CHU/2018-19/ W1.02624 | Const.of Class room. Muslim para PS. | 7263781 | 01.11.18 | 12.11.18 | 27.11.18 | 13.12.18 | 23.12.18 | 6900591.95 | M/S Prince Biswas Traders | 28.01.19 | 31.10.19 |  | 40% |  |  | - | - | - | -
e-Tender/ NBIDNNGPS/CHU/CHU/2018-19/ W1.02625 | Const.of Class room. Subodhpur Boalmary PS. | 7919411 | 01.11.18 | 12.11.18 | 27.11.18 | 13.12.18 | 23.12.18 | 7523440.45 | M/S Ayesha Enterprise | 28.01.19 | 31.10.19 |  | 30% |  |  | - | - | - | -
e-Tender/ NBIDNNGPS/CHU/CHU/2018-19/ W1.02626 | Const.of Class room. Jugirhuda PS. | 8149215 | 01.11.18 | 12.11.18 | 03.12.18 | 20.12.18 | 03.01.19 | 7741754.25 | M/S N.N Construction | 07.02.19 | 10.11.19 |  | 40% |  |  | - | - | - | -
e-Tender/ NBIDNNGPS/CHU/CHU/2018-19/ W1.02627 | Const.of Class room. Khaspara PS. | 8088011 | 01.11.18 | 12.11.18 | 03.12.18 | 20.12.18 | 03.01.19 | 7683610.45 | Md.Alauddin | 07.02.19 | 10.11.19 | - | 25% |  |  | - | - | - | -
e-Tender/ NBIDNNGPS/CHU/CHU/2018-19/ W1.02792 | Const.of Class room. Jhoraghata P.S. | 7447099 | 12.11.18 | 22.11.18 | 10.12.18 | 03.01.19 | 16.01.19 | 7074744 | Md. Agirbar Rahman | 18.02.19 | 21.11.19 | - | 35% |  |  | - | - | - | -
e-Tender/ NBIDNNGPS/CHU/CHU/2018-19/ W1.00657 | Const.of Class room. Gopinathpur P.S. | 9266573 | 18.12.18 | 06.01.19 | 24.01.19 | 14.02.19 | - | 8803244.35 | M/S Firoz Enterprise | 27-03-19 | 1919-12-26 | - | 0% |  |  | - | - | - | -
| Accountant | [6 empty] | Sub-Asstt. Engineer | [7 empty] | Upazila Engineer
| Chuadanga Sadar | [6 empty] | Chuadanga Sadar | [7 empty] | Chuadanga Sadar
| Chuadanga. | [6 empty] | Chuadanga. | [7 empty] | Chuadanga.
2

## Sheet2
Project Name : NBIDNNGPS-1
On line Approved Scheme List (School wise details e-Tender Information)
|  | Region: Jashore. |  |  |  |  | District: Chuadanga.
Upazila: Chuadanga Sadar
Package | School Code | Sl. | School Name | Estimated Cost | Room No | Topo Send to H/Q.Date | Soil Send to H/Q.Date | Package Sending Date | APP Sending Date | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
W1.00228 | 20304020402 | 1 | Aria | 6803252 | 5 | 04.12.17 | 04.12.17 | 31.12.17 | 4.2.18
W1.00229 | 99203049006 | 2 | Chandipur Malik Sharani | 6676753 | 5 | 04.12.17 | 04.12.17 | 31.12.17 | 4.2.18
W1.00230 | 99203049005 | 3 | Nafar kandi | 6547290 | 5 | 04.12.17 | 04.12.17 | 31.12.17 | 4.2.18
W1.00231 | 99203049002 | 4 | Police Line | 7721076 | 5 | 04.12.17 | 04.12.17 | 31.12.17 | 4.2.18
W1.00433 | 99203049003 | 5 | Jibna | 7301302 | 5 | 04.12.17 | 04.12.17 | 12.02.18 | 14.03.18
W1.00902 | 20304080802 | 6 | Motiar Rahman Malik | 6606865 | 5 | 18.12.17 | 18.12.17 | 01.04.18 | 17.04.18
2
Monthly Target of Physical Progress for Primary School Construction work
Region: Jashore. |  |  | District: Chuadanga. |  |  | Upazila Name: Chuadanga Sadar |  |  | (NBIDGPS)
Package | School Name | Targeted Physical Progress (%) | [5 empty] | Estimated Cost/ Contract Value | Targeted Total Expenditure upto June-19 (FY-2017-18 and FY-2018-19) | Remarks
|  | Jan | Feb | Mar | April | May | June
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
e-Tender/NBIDGPS/ CHD/ SAD /2017-18//W1.00166 | Gaidghat | 80 | 100 |  |  |  |  | 6571617 | 6571617
e-Tender/NBIDGPS/CHD/ SAD/2017-18//W1.00167 | Akandda Baria | 95 | 100 |  |  |  |  | 5959836 | 5959836
e-Tender/NBIDGPS/CHD/ SAD/2017-18//W1.00168 | Alokdia | 80 | 100 |  |  |  |  | 6571617 | 6571617
e-Tender/NBIDGPS/CHD/ SAD/2017-18//W1.00169 | 1.No. Chuadanga | 95 | 100 |  |  |  |  | 6758597 | 6758597
e-Tender/NBIDGPS/CHU/ SAD/2018-19//W1.02927 | Boalmary | [6 empty] | 7459190 | 4500000 | NOA Issued date 13.01.19
e-Tender/NBIDGPS/CHU/ SAD/2018-19//W1.03159 | Teghori | [6 empty] | 8928185 | 5400000 | Tender Evalation under prosses
[8 empty] | Sum (a) | 35761667
[6 empty] | Expenditure Up to 30.06.2018 (B) |  |  | 11300000
[5 empty] | Total Tergeted Expenditure for FY: 2018-19 |  |  | (c=a-b) | 24461667
Total Fund Released Taka (FY: 2018-19) = 6000000.00, Up to Date Total Expenditure TK.(FY:2018-19)=6000000.00,Fund Demand Now Tk.18461667.00
Upazila Engineer
Chuadanga Sadar
Chuadanga.
Sheet-2
|  | Monthly Target of Physical Progress for Primary School Construction work | [8 empty] | 3
Region: Jashore. |  |  | District: Chuadanga. |  |  | Upazila Name: Chuadanga Sadar |  |  | (NBIDNNGPS)
Package | School Name | Targeted Physical Progress (%) | [5 empty] | Estimated Cost/Contract Value | Targeted Total Expenditure upto June-19 (FY-2017-18 and FY-2018-19) | Remarks
|  | Jan | Feb | Mar | April | May | June
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
e-Tender/NBIDNNGPS/CHD/ SAD/2017-18//W1.00228 | Aria | 85 | 90 | 95 | 100 |  |  | 6122926 | 6122926
e-Tender/NBIDNNGPS/CHD/ SAD/2017-18//W1.00229 | Chandipur Malik Sharani | 95 | 100 |  |  |  |  | 6009077 | 6009077
e-Tender/NBIDNNGPS/CHD/ SAD/2017-18//W1.00230 | Nafarkandi | 95 | 100 |  |  |  |  | 5892561 | 5892561
e-Tender/NBIDNNGPS/CHD/ SAD/2017-18//W1.00231 | Pollice Line | 95 | 100 |  |  |  |  | 6948968 | 6948968
e-Tender/NBIDNNGPS/CHD/ SAD/2018-19//W1.00433 | Jibna | 40 | 60 | 80 | 90 | 100 |  | 6936234 | 6936234
e-Tender/NBIDNNGPS/CHD/ SAD/2018-19//W1.00902 | Motiar Rahman Malik | 40 | 60 | 80 | 100 |  |  | 6276521 | 6276521
e-Tender/NBIDNNGPS/CHU/ CHU/2018-19//W1.02622 | Mohammad jomma | [6 empty] | 8272526 | 5000000 | NOA Issued date 03.01.19
e-Tender/NBIDNNGPS/CHU/ CHU/2018-19//W1.02623 | Sankarchundra Sonirvor | [6 empty] | 7581871 | 4600000 | do
e-Tender/NBIDNNGPS/CHU/ CHU/2018-19//W1.02624 | Muslimpara | [6 empty] | 6900591 | 4200000 | NOA Issued date 02.01.19
e-Tender/NBIDNNGPS/CHU/ CHU/2018-19//W1.02625 | Subodhpur boalmari | [6 empty] | 7523440 | 4600000 | NOA Issued date 03.01.19
e-Tender/NBIDNNGPS/CHU/ CHU/2018-19//W1.02626 | Jugirhuda | [6 empty] | 7741754 | 4700000 | NOA Issued date 13.01.19
e-Tender/NBIDNNGPS/CHU/ CHU/2018-19//W1.02627 | Khaspara | [6 empty] | 7683610 | 4600000 | do
Package | School Name | Targeted Physical Progress (%) | [5 empty] | Estimated Cost/Contract Value | Targeted Total Expenditure upto June-19 (FY-2017-18 and FY-2018-19) | Remarks | 4
|  | Jan | Feb | Mar | April | May | June
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
e-Tender/NBIDNNGPS/CHU/ CHU/2018-19//W1.02792 | Jhoraghata | [6 empty] | 7074744 | 4300000 | Tender Evalation under prosses
e-Tender/NBIDNNGPS/CHU/ CHU/2018-19//W1.00657 | Gopinathpur | [6 empty] | 8803244 | 5300000 | Tender prosses
[8 empty] | Sum (a) | 75486297
[6 empty] | Expenditure Up to 30.06.2018 (B) |  |  | 15804000
[5 empty] | Total Tergeted Expenditure for FY: 2018-19 |  |  | (c=a-b) | 59682287
Total Fund Released Taka (FY: 2018-19) = 18500000.00, Up to Date Total Expenditure TK.(FY:2018-19)=6661168.00,Fund Demand Now Tk.41182287.00
Upazila Engineer
Chuadanga Sadar,Chuadanga.
Sheet-2

## PEDP-III
Local Government Engineering Department
Need Based Infrastructural Development of Government Primary School (1st Phase) (NBIDGPS)
[6 empty] | Detail Contract Progress Report | [8 empty] | Month of August/2018
Upazila¦ Chuadanga Sadar |  |  | District: Chuadanga.
Package No | Name of Primary School | Estimated Cost | Scheme Approved Date | APP Approved Date | Tender Publication Date | Tender Opening Date | Date of Evaluation | Contract Amount | Name of Contractor | Date of Contract | Date of Completion | Phy.Prog. |  |  |  | Amount Spent (Const. Works) | Fund Demand | Soil test
[12 empty] | Actual | Targeled by UE
[13 empty] | June | Jaly | August
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
e-Tender/ NBIDGPS/CHD/SAD/ 2017-18/ W1.00166 | Const.of Class room of Gaidghat GPS. | 7301797 | 07.12.17 | 1.1.18 | 16.1.18 | 13.02.18 | 26.02.18 | 6571617.3 | M/S. Liton Traders | 26.04.18 | 31.01.19 |  |  |  | 30% |  |  | 27500
e-Tender/ NBIDGPS /CHD /SAD/ 2017-18/ W1. 00168 | Const.of Class room of Alokdia GPS. | 7301797 | 7.12.17 | 1.1.18 | 16.1.18 | 13.02.18 | 26.02.18 | 6571617.3 | M/S. Liton Traders | 26.04.18 | 31.01.19 |  |  |  | 30% |  |  | 27500
e-Tender/ NBIDGPS/CHD/SAD/ 2017-18/ W1.00167 | Const.of Akandabaria GPS. | 6622041 | 10.01.18 | 04.02.18 | 27.02.18 | 28.03.18 | 10.04.18 | 5959836.9 | Mozahar Enterprise (PVT)LTD. | 13.05.18 | 12.02.19 |  | 15% | 87% | 87% | 5131773 |  | 27500
e-Tender/ NBIDGPS/CHD/SAD/ 2017-18/ W1.00169 | Const.of 1 No. Chuadanga GPS. | 7509553 | 10.01.18 | 04.02.18 | 27.02.18 | 28.03.18 | 10.04.18 | 6758597.7 | Mozahar Enterprise (PVT)LTD. | 13.05.18 | 12.02.19 |  | 10% | 92% | 92% | 6168227 |  | 27500
| Total Tk. | 28735188 | [5 empty] | 25861669.2 | [7 empty] | 11300000 |  | 110000
Project Name : NBIDGPS-1
On line Approved Scheme List (School wise details e-Tender Information)
|  |  | Region: Jashore. |  |  |  |  | District: Chuadanga.
| Package |  | School Code | Sl. | School Name | Estimated Cost | Room No | Topo Send to H/Q.Date | Soil Send to H/Q.Date | Package Sending Date | APP Sending Date | Remarks
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
|  | W1.00166 | 91203040811 | 1 | Gaid Ghat | 7301797 | 5 | 9.10.17 | 9.10.17 | 7.12.17 | 1.1.18
|  | W1.00168 | 91203040202 | 2 | Alokdia | 7301797 | 5 | 9.10.17 | 9.10.17 | 7.12.17 | 1.1.18
|  | W1.00167 | 91203040602 | 3 | Akandabaria | 6622041 | 4 | 9.10.17 | 9.10.17 | 10.01.18 | 4.2.18
|  | W1.00169 | 91203040101 | 4 | 1 No. Chuadanga | 7509553 | 5 | 9.10.17 | 9.10.17 | 10.01.18 | 4.2.18
Project Name : NBIDNNGPS-1
Need Based Infrastructural Development of Government Primary School (1st Phase)
Detail Contract Progress Report
Upazila¦ Chuadanga Sadar |  | 2: District: Chuadanga.
Package Code | Name of Primary School | Estimated Cost | No of Tender Called | Date of IFT | Date of Tender Received | Date of Evaluation | Date of NOA Issuing | Contract Amount | Revised Contract Amount | Name of Contractor | Date of Contract | Date of Completion | Actul prog (%) | Tergeted by UE |  |  |  | Remarks
[14 empty] | Sept | Oct | Nove | Dec
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
W1.00228 | Const.of Class room of Gaidghat GPS. | 7301797 | 1st called | 1.1.18 | 16.1.18 | 13.02.18 | 26.02.18 | 6571617.3 | 0 | M/S. Liton Traders | 26.04.18 | 31.01.19 | 30% | 40% | 50% | 70% | 80%
W1. 00168 | Const.of Class room of Alokdia GPS. | 7301797 | 1st called | 1.1.18 | 16.1.18 | 13.02.18 | 26.02.18 | 6571617.3 | 0 | M/S. Liton Traders | 26.04.18 | 31.01.19 | 30% | 40% | 50% | 70% | 80%
W1.00167 | Const.of Akandabaria GPS. | 6622041 | 1st called | 04.02.18 | 27.02.18 | 28.03.18 | 10.04.18 | 5959836.9 | 0 | Mozahar Enterprise (PVT)LTD. | 13.05.18 | 12.02.19 | 87% | 90% | 90% | 95% | 100%
W1.00169 | Const.of 1 No. Chuadanga GPS. | 7509553 | 1st called | 04.02.18 | 27.02.18 | 28.03.18 | 10.04.18 | 6758597.7 | 0 | Mozahar Enterprise (PVT)LTD. | 13.05.18 | 12.02.19 | 92% | 92% | 95% | 0.98 | 100%
| Total Tk. | 1: 28735188; 7: 25861669.2
Local Government Engineering Department
Need Based Infrastructural Development of Newly Nationlized Government Primary School (1st Phase) (NBIDNNGPS)
|  | 5: Detail Contract Progress Report |  |  | Month of August/2018
Upazila¦ Chuadanga Sadar |  | 2: District: Chuadanga.
Package No | Name of Primary School | Estimated Cost | Scheme Approved Date | APP Approved Date | Tender Publication Date | Tender Opening Date | Date of Evaluation | Contract Amount | Name of Contractor | Date of Contract | Date of Completion | Phy.Prog. |  |  |  | Amount Spent (Const. Works) | Fund Demand | Soil test
|  | 11: Actual | Targeled by UE
[13 empty] | June | July | August
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
e-Tender/ NBIDNNGPS/CHD/SAD/ 2017-18/ W1.00228 | Const.of Aria RNGPS | 6803252 | 31.12.17 | 04.02.18 | 19.02.18 | 14.03.18 | 27.03.18 | 6122926.8 | Mozahar Enterprise (PVT)LTD. | 03.05.18 | 08.05.19 |  | 64% | 64% | 64% | 3904000 |  | 27500
e-Tender/ NBIDNNGPS/ CHD/SAD/ 2017-18/ W1.00229 | Const.of Chandipur Malik Sharani GPS | 6676753 | 31.12.17 | 04.02.18 | 19.02.18 | 14.03.18 | 27.03.18 | 6009077.7 | Mozahar Enterprise (PVT)LTD. | 03.05.18 | 08.05.19 |  | 67% | 67% | 67% | 4000000 |  | 27500
e-Tender/ NBIDNNGPS/CHD/SAD/ 2017-18/ W1.00230 | Const.of Nafarkandi RNGPS | 6547290 | 31.12.17 | 04.02.18 | 19.02.18 | 14.03.18 | 27.03.18 | 5892561 | Mozahar Enterprise (PVT)LTD. | 03.05.18 | 08.05.19 |  | 67% | 67% | 67% | 3900000 |  | 27500
e-Tender/ NBIDNNGPS/CHD/SAD/ 2017-18/ W1.00231 | Const.of Police Nine RNGPS | 7721076 | 31.12.17 | 04.02.18 | 19.02.18 | 14.03.18 | 27.03.18 | 6948968.4 | Mozahar Enterprise (PVT)LTD. | 03.05.18 | 08.05.19 |  | 58% | 58% | 70% | 4000000 |  | 27500
e-Tender/ NBIDNNGPS/CHD/SAD/ 2017-18/ W1.00433 | Jibna | 7301302 | 12.02.18 | 14.03.18 | 27.03.18 | 18.04.18 | 03.05.18 | 6936234.25 | Shohag Enterprise | 27.05.18 | 31.05.19 |  |  | 10% | 10% |  |  | 27500
e-Tender/ NBIDNNGPS/CHD/SAD/ 2017-18/ W1.00902 | Motir Rahman Malik | 6606865 | 01.04.18 | 17.04.18 | 26.04.18 | 16.05.18 | 21.05.18 | 6276521.75 | M/S.Proma Traders | 21.06.2018 | 30.04.19 |  |  | 10% | 10% |  |  | 27500
|  | 1: 41656538; 7: 38186289.9 |  |  |  | 15804000 |  | 165000

## Muktijoddha-2
Upazila Muktijoddha Complex Project
Local Government Engineering Department
Monthly Progress Report
| District: Chuadanga | [9 empty] | For the Month of : |  |  | April'2019
Sl.No | Name of Upazila | Package No | Name of Scheme | Name of Contractor | Approved Estimated Cost | Contract Amount | Date of Contract | Date of Completion | Actual date of Completion | Fund Received | Fund Spent | Prog.In this Month (%) | Prog.upto this Month (%) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Chuadanga Sadar | CUMCP/CHU/SAD/17/C-334 | Const.of Upazila Muktijoddha Complex Bhaban under Chuadanga Sadar Upazila in the District of Chuadanga. | Mozahar Enterprise (PVT) LTD. | 197.4 | 177.66 | 15.10.17 | 08.06.18 | - | - | - | 100% | 100% | ‡gŠRvi bvgt †gŠRv-42 bs PzqvWv½v, `vM bs-9108, LwZqvb bs-01
| Accountant |  |  |  | Sub-Assistant Engineer |  |  |  |  | Upazila Engineer
| LGED,Chuadanga |  |  |  | LGED,Chuadanga. |  |  |  |  | LGED,Chuadanga.

## GSIDP
Montly Progress Report
Name of Project: GSIDP | [10 empty] | 1
| Upazila: Chuadanga Sadar | District: Chuadanga. | [5 empty] | Division Name : Khulna
[8 empty] | For the Month of: |  | April'2019
Sl.No | Package No | Name of Scheme | Estimated Cost (TK) | Date of Contract | Contract Price (Tk) | Contractor Name | Date of Commncement | Date of Completion | Physical Progress (%) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | GSIDP/CHU/DW-40 | Improvement of Islam para Jame Mosque. | 486444 | 28.11.18 | 462121.8 | Agrozatra Enterprise,Chuadanga. | 04.12.18 | 22.05.19 | 100%
2 | GSIDP/CHU/DW-21 | Improvement of Guideghate Dakkin para Jame Mosque. | 1392098 | 09.12.18 | 1322493.1 | M/S. Jaman Traders, Damurhuda,Chuadanga. | 15.12.18 | 02.06.19 | 60%
3 | GSIDP/CHU/DW-42 | Improvement of Chuadanga Rail Bazar OIC Jame Mosque. | 312681 | 05.12.18 | 297046.95 | M/S. Nitu Traders,Chuadanga. | 11.12.18 | 29.05.19 | 100%
4 | GSIDP/CHU/DW-43 | Improvement of Maserdair Graveyard. | 1325574 | 10.12.18 | 1259295.3 | Md.Rezaul Haque Railpara,Chuadanga. | 16.12.18 | 03.06.19 | 40%
5 | GSIDP/CHU/DW-37 | Improvement of Chuadanga Porotun Gorostan Jame Mosque. | 2334619 | 21.10.18 | 2217888.05 | Md.Rezaul Haque Railpara,Chuadanga. | 27.10.18 | 25.04.19 | 100%
6 | GSIDP/CHU/DW-41 | Improvement of Hazrahati Uttarpara Baitul Mamur Jame Mosque. | 312793 | 23.12.18 | 297153.35 | M/S. Shariful Islam, Arappur, Jhenaidah. | 26.12.18 | 16.06.19 | 100%
7 | GSIDP/CHU/DW-51 | Improvement of NehalpurPurbopara Bytulkarim Jame Mosque. | 350401 | 29.01.19 | 332880.95 | Akteruzzaman Traders Damurhuda Chuadanga | 04.02.19 | 03.08.19 | 100%
8 | GSIDP/CHU/DW-52 | Improvement of Dehi Mazarpara Waktia Mosque. | 374752 | 30.01.19 | 356014.4 | Md.Hider Ali Jibonnagar,Chuadanga | 05.02.19 | 04.08.19 | 100%
9 | GSIDP/CHU/DW-48 | Improvement of Furshedpur Jame Mosque. | 303063 | 29.01.19 | 287909.85 | Agrozatra Enterprise,Chuadanga. | 04.02.19 | 03.08.19 | 100%
10 | GSIDP/CHU/DW-54 | Improvement of Titudah Baganpara Jame Mosque. | 301006 | 30.01.19 | 285955.7 | Md.Abu Zafur Montu,Chuadanga. | 05.02.19 | 04.08.19 | 100%
11 | GSIDP/CHU/DW-49 | Improvement of Kundipur Jame Mosque. | 323463 | 10.02.19 | 307289.85 | M/S Parvin Traders,Chuadanga. | 16.02.19 | 15.08.19 | 50%
12 | GSIDP/CHU/DW-50 | Improvement of Bolia Aak Center(Bazar)Wakto Mosque. | 383149 | 06.02.19 | 363991.55 | N Enterprise ,Chuadanga. | 12.02.19 | 11.08.19 | 100%
13 | GSIDP/CHU/DW-55 | Improvement of Sujaetpur Jame Mosque. | 312375 | 10.02.19 | 296756.25 | M/S Parvin Traders,Chuadanga. | 16.02.19 | 15.08.19 | 10%
14 | GSIDP/CHU/DW-59 | Improvement of Boalmari Porchim para Jame Mosque. | 465418 | 04.02.19 | 442147.1 | N Enterprise ,Chuadanga. | 10.02.19 | 09.08.19 | 70%
15 | GSIDP/CHU/DW-62 | Improvement of Gaidghat Uttarpara (Majhar Para) Jame Mosque. | 484251 | 03.02.19 | 460038.45 | Md Habibur Rahaman,Chuadanga. | 09.02.19 | 08.08.19 | 0%
16 | GSIDP/CHU/DW-64 | Improvement of Makaldanga Bisho Dharma Kandro Graveyard. | 312813 | 10.02.19 | 297172.35 | M/S Parvin Traders,Chuadanga. | 16.02.19 | 15.08.19 | 80%
17 | GSIDP/CHU/DW-56 | Improvement of Sorabaria Jame Mosque. | 381006 | 07.02.19 | 361955.7 | Titu Enterprise Damurhuda,Chuadanga. | 13.02.19 | 12.08.19 | 100%
18 | GSIDP/CHU/DW-57 | Improvement of Goritupi Bazar Jame Mosque. | 350074 | 05.02.19 | 332750.3 | M/S.Alamin Construction Jhenaidah. | 11.02.19 | 10.08.19 | 100%
19 | GSIDP/CHU/DW-63 | Improvement of Belgachi Bitul Falak Jame Mosque. | 492355 | 28.01.19 | 467737.25 | M/S.Pintu Traders Jhenidah. | 03.02.19 | 02.08.19 | 100%
20 | GSIDP/CHU/DW-61 | Improvement of Jintola Jame Mosque. | 325396 | 27.01.19 | 301926.2 | M/S.Shariful Islam Arappur Jhenidah. | 02.02.19 | 01.08.19 | 100%
21 | GSIDP/CHU/DW-60 | Improvement of Atimkhana Jame Mosque. | 504913 | 27.01.19 | 479667.35 | M/S.Shariful Islam Arappur Jhenidah. | 02.02.19 | 01.08.19 | 100%
22 | GSIDP/CHU/DW-65 | Improvement of Bhultia Sikirpara Graveyard. | 1000000 | 12.02.19 | 950000 | Md Abdul Wahed Jibonnagar Chuadanga. | 18.02.19 | 17.08.19 | 60%
23 | GSIDP/CHU/DW-79 | Improvement of Pirpur Bitul Mamur-Jame Mosque | 1479105 | 11.02.19 | 1405149.75 | Md Abdulla Al Mamun Chuadanga. | 17.02.19 | 16.08.19 | 50%
24 | GSIDP/CHU/DW-53 | Improvement of Jhajri Utterpara-Jame Mosque | 307257 | 07.02.19 | 291894.15 | Titu Enterprise Chuadanga. | 13.02.19 | 12.08.19 | 90%
| Accountant |  | Sub-Asstt.Engineer |  |  |  |  | Upazila Engineer
| LGED |  | LGED |  |  |  |  | LGED
| Chuadanga Sadar,Chuadanga. |  | Chuadanga Sadar,Chuadanga. |  |  |  |  | Chuadanga Sadar,Chuadanga.

## Land Office
Montly Progress Report
Name of Project: Construction of Town and Union Land Office Across the Country under Ministry of Land.
| Upazila: Chuadanga Sadar | District: Chuadanga. | [5 empty] | Division Name : Khulna
[8 empty] | For the Month of : |  | April'2019
Sl.No | Name of work | Namber of Land Office | Estimated Cost (TK) | Date of Contract | Contract Price (Tk) | Contractor Name | Completion Date | Physical Progress (%) | Payment Made (Tk) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Construction of Mominpur Union Land Office (Including 180m Boundary Wall and Barbed wire fencing) and Chuadanga Pour Land Office (Including 109m Boundary Wall ) at Sadar Upazila in Chuadanga District.under Construction of Town and Union Land Office Across the Country Project. | 2 | 9787000 | 12.03.18 | 8808300 | Mozahar Enterprise (PVT.)LTD,Khanjahan Ali road,Khulna. | 14.01.19 | 90%
| Accountant |  | Sub-Asstt.Engineer |  |  |  |  | Upazila Engineer
| LGED |  | LGED |  |  |  |  | LGED
| Chuadanga Sadar,Chuadanga. |  | Chuadanga Sadar,Chuadanga. |  |  |  |  | Chuadanga Sadar,Chuadanga.

## NBIDGPS-1
Local Government Engineering Department
Need Based Infrastructure Development of Newly Nationalized Govt. Primary School (1st phase) (NBIDNNGPS-1)
Details Contract Progress Report
| District: Chuadanga |  |  |  | Upazila: Chuadanga Sadar. |  |  |  |  | Date: May/2018 |  |  |  | Taka in Lac.
SL.No. | Name of Primary School | Estimated cost | Room (Nos) | SoilTopo Sending to HQ(Date) | Admin Approval (Date) | App Approval (Date) | Tender ID | IFT (Date) | Tender Evul (Date) | Contract Amount | Date of Cont | Date of Comp | Phy prog | Amount Spent | Amount Spent (Soil) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Aria | 68.03 | H-5 | 4.12.17 | 31.12.17 | 04.02.18 | 164568 | 15.02.18 | 27.03.18 | 6122926.8 | 03.05.2018 | 08.05.2019 | 10% | 15%
2 | Chandipur Malik Sharani | 66.76 | H-5 | 1.12.17 | 31.12.17 | 04.02.18 | 134968 | 15.02.18 | 27.03.18 | 6009077.7 | 03.05.2018 | 08.05.2019 | 10% | 20%
3 | Nafarkaandi | 65.47 | H-5 | 4.12.17 | 31.12.17 | 04.02.18 | 164991 | 15.02.18 | 27.03.18 | 5892561 | 03.05.2018 | 08.05.2019 | 15% | 20%
4 | Police Line | 77.21 | H-4 V-1 | 4.12.17 | 31.12.17 | 04.02.18 | 165288 | 15.02.18 | 27.03.18 | 6948968.4 | 03.05.2018 | 08.05.2019 | 10% | 20%
5 | Jibna | 73.01 | H-5 | 4.12.17 | 12.02.18 | 14.03.18 | 178279 | 25.03.18 | 30.04.18 | 6936234.25 |  |  | 0% |  |  | NOA Issued 07.05.18
6 | Motair Rahman Malik | 66.06 | H-5 | 18.12.17 | 01.04.18 | 17.04.18 | 189774 | 23.04.18 | [7 empty] | Tender Received Shall be 16.05.18
| Total Tk. | 416.54 | [7 empty] | 31909768.15
|  | Accountant |  |  |  | Sub-Asstt. Engineer | [5 empty] | Upazila Engineer
|  | Chuadanga Sadar |  |  |  | Chuadanga Sadar | [5 empty] | Chuadanga Sadar
|  | Chuadanga, |  |  |  | Chuadanga, | [5 empty] | Chuadanga,
Local Government Engineering Department
Need Based Infrastructure Development of Govt. Primary School (1st phase) (NBIDGPS-1)
Details Contract Informations Report
| District: Chuadanga |  |  |  | Upazila: Chuadanga Sadar. |  |  |  |  | Date: 08.05.2018 |  |  |  | Taka in Lac.
SL.No. | Name of Primary School | Estimated cost | Room (Nos) | SoilTopo Sending to HQ (Date) | Admin Approval (Date) | App Approval (Date) | Tender ID | IFT (Date) | Tender Evul (Date) | Contract Amount | Date of Contrect | Date of Completetion | Phy prog | Amount Spent | Amount Spent (Soil) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Gaidghat | 73.01 | H-5 | 09.10.17 | 07.12.17 | 01.01.18 | 151758 | 14.01.18 | 26.02.18 | 6571617.3 | 26.04.2018 | 31.01.2019 | 10%
2 | Alukddia | 73.01 | H-5 | 09.10.17 | 07.12.17 | 01.01.18 | 151758 | 14.01.18 | 26.02.18 | 6571617.3 | 26.04.2018 | 31.01.2019 | 10%
3 | Akandabaria | 66.22 | H-4 | 09.10.17 | 10.01.18 | 04.02.18 | 168216 | 25.02.18 | 10.04.18 | 5959836.9 |  |  | 10% |  |  | NOA Issuced 15.04.18
4 | 1 No. Chuadanga | 75.09 | H-2 V-3 | 09.10.17 | 10.01.18 | 04.02.18 | 168229 | 25.02.18 | 10.04.18 | 6758597.7 |  |  | 10% |  |  | NOA Issuced 15.04.18
| Total Tk | 287.33 | [7 empty] | 25861669.2
| Accountant |  |  |  | Sub-Asstt. Engineer | [5 empty] | Upazila Engineer
| Chuadanga Sadar |  |  |  | Chuadanga Sadar | [5 empty] | Chuadanga Sadar
| Chuadanga, |  |  |  | Chuadanga, | [5 empty] | Chuadanga,
NBIDGPS-1