**District Integrated Bottom-up Plan for Satkhira, LCBCE – Project-2016**

| Sl# | **Children Problems** | **Area to be concentration** | **Actions to be taken/ Activity** | **Responsible** **department / person** | **Approx. Budget** | **Target Beneficiaries** | **Indicator of achievement/ Result** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Ashashuni** | **Shyamnagar** | **Ashashuni** | **Shyamnagar** |
| **Education Section** |  |  |  |  |  |  |  |  |
| 1 | About 50% parents do not know the appropriate age for enrolling in PPE  | two union | 10 union | To increase awareness of parents through house visit by school teachers. UP and SMC members and FWA can do it during house visit.  | School teachers, SMC, AUEO, CUP, FPI, FWA  | 40,000 | 150,000 | Children and their Parents  | To increase enrolment rate |
| 2 | Lack of coordination among the GO and NGO run PPE. | All union | All union | To ensure quarterly coordination meeting between GO and relevant NGOs officials at Upazila | UEO and NGO representative | 275,000 | 300,000 | GoB and NGO officials | To avoid duplication and ensuring timely coordination meeting held |
| 3 | Maximum PPE class do not have trained teachers  | About 50% GPS | About 50% GPS | To organize training for the teachers | AUEO, URC, DPEO | - | - | PPE teachers | To ensure trained teachers at class room |
| 4 | Shortage of class room in school  | **86** School list attached  | **42** School list attached in annex-1 | Build additional one class room for each school | DPEO, UEO, UNO | 21,465,000 | 6,770,000 | School students | To ensure one additional class room |
| 5 | Shortage of furniture in school | **96** School list are attached  | **53** School list are attached  | Furniture supply required to respective school | DPEO, UEO, CUP | 3,718,000 | 2,260,000 | School students | To ensure adequate number of furniture |
| 6 | Inadequate facilities of safe drinking water and Sanitation | **120** School list are attached | **43** School list are attached  | Install safe water point and build required toilet in respective GPS | DPEO, XEN-DPHE, UNO | 20,873,000 | 10,090,000 | School students | To ensure safe water point and sanitation facilities.  |
| 7 | In GPS, the teachers are irregular. | About 50% school | About 50% school | To ensure teachers at the class room in time | H. Teacher, SMC, AUEO, UEO | -- | --- | School teacher | To ensure teachers attendance in time at School |
| 8 | Shortage of TL material, not use of TL | **64** School list are attached | **53** School list are attached | To ensure develop and use of TL materials by class teacher.  | Teachers, H. Teacher AUEO  | 1,957,000 | 2,246,000 | Class teachers | To ensure availability and use of TL materials and quality education  |
| 9 | Less scope to play in school ground | **54** School list attached | **45** School list are attached | Improve the playground by earth filling  | SMC, AUEO, UEO, CUP | 2,339,700 | 2,100,000 | School students | Create scope to play in good playground for children |
| 10 | Attendance rate low due to lack of road facility | 45 School list attached | **38** School list are attached | School connecting road re-construction/ brick soling/carpeting required | LGED and UP | 4,690,000 | 6,700,000 | School students | Attendance rate will increase specially in rainy session.  |
| 11 | About 70% GPS not child friendly  | All union | All union | 53 GPS need to develop as child friendly school | DPEO, LGED UEO | 5,100,000 | 5,300,000 |  |  |
| Birth Registration |
| 1 | Shortage of BR application form  | Three union | --- | BR application form have to available in UP Office.  | UP Office.  | 45,000 | -- | Community people, Parents, UP rep. Health & FP staffs  | Increase the BR rate Meeting Agenda; Attendance sheet, Meeting minutes |
| 2 | People are not aware about child rights | All union | All union | Organize different day observance on child rights issues  | UP, Upazila and District administration | 350,000 | 360,000 |
| 3 | The parents don’t see any importance of BR within 45 days of birth until they need the birth certificate for get any service | All union | All union | Awareness build-up of parents on importance of BR in time. It can be done during ward shova and any social gathering. FWA can do it during house visit. | Union Parishad | 250,000 | 255,000 | Parente of Children | To increase BR rate within 45 days of birth in each union. |
| 4 | Lack of coordination and clarity between Health, Family planning and UP on their role.  | All union | All union | Organize coordination meeting at union level.  | UP Chairman | 125,000 | 180,000 | UP Rep, health & FP union level staffs  | Increase the BR rate, Get clear conception on their role.  |
| 5 | Some parents are not able to fill-up the BR application form so they not apply on time. | 4 union | 5 union | EPI worker as the first contact person for new born babies. They can help to the parents in filling up the forms, UP will provide BR application form to HA.  | UP and HA, AHI, FWA | -- | -- | Children those age is up to 45 days | Increase the BR rate of children. BR application fill-up form are available in UP office. |
| **Health** |
| 1 | About 20% people lack of knowledge on benefits of immunization and diseases prevented by vaccines.  | All union | All union | Increase knowledge through mass awareness campaign, counselling at Immunization Centre by HA and house visit by FWA  | HA, AHI and FWA | 250,000 | 260,000 | Parents of children | Immunization rate will increase, Counselling session held regularly.  |
| 2 | Some cases older members of the family discourage immunization.  | All union | All union | Build awareness through house visit and discussion in ward sova | HA, AHI, FWA, MUP | 150,000 | 170,000 | Community people | Immunization rate will increase |
| 3 | Lack of house to house follow up by health workers to find out drop outs. | All union | All union | House visit will perform regularly and find out the drop outs | HA, AHI, FWA | - | - | Children Age up to 23 month | Immunization rate will increase |
| 4 | Lack of supportive supervision at the field level.  | All union | All union | Increase field visit by the supervisor and assist to field worker  | AHI, HI, UH&FPO | - | - | HA, FWA and children | Immunization rate will increase |
| 5 | Difficulty in reaching the immunization sites during rainy season | 46 connecting road in all union | 25 connecting road in all union | Increase the Immunization Centre for rainy season and reconstruction of road  | HI, UH&FPO | 4,590,000 | 4,950,000 | Children | Immunization rate will increase |
| 6 | Shortage of health workers at field level. | All union | All union | Fill-up the vacant position  | CS and UH&FPO | -- | -- | Children  | Immunization rate will increase |
| 7 | Shortage of Community Clinic | 29 nos. CC in all union | 27 nos. CC in all union | Increase one CC in each union | CS and UH & FPO | 11,600,000 | 5,300,000 | Children and pregnant women | Immunization, ANC and other health service will improve |
| **Nutrition** |
| 1 | Poor knowledge of mothers and family members on ANC and effect of IFA on pregnancy outcome | All union | All union | Increase counselling and courtyard meeting  | FP departmentFWA, HA | 275,000 | 280,000 | Pregnant mothers  | ANC received and IFA intake rate will increase. Attendance increase in FWC and CC |
| 2 | In many cases mothers were not permitted by husbands or mothers in law to go out of home for check-up/ ANC | All union | All union | Increase counselling, house visit courtyard meeting and awareness build-up through discussion in ward sova. Mass campaign | FP departmentFWA, HA, FPI, AHI, MUP | 275,000 | 280,000 | Husbands & mother in low of pregnant women  | Increase right holders at health Centre’s and ANC rare |
| 3 | Service Centre’s were not close to the villages and road infrastructure was not good | All union | All union | Construction/re-construction/repairing of infrastructure | LGED, UP | Included in health section | Included in health section | Pregnant mothers and children | Attendance rate will increase in service center, Good communication facility available in community |
| 4 | Shortage of Field worker (FWA) | All union | All union | Fill-up the vacant position | FP, departmentDD-FP | -- | -- | Pregnant mothers, children | Increase right holder attendance and improve quality of service |
| 5 | Lack of coordination and clarity between Health, Family planning and UP on their role. | All union | All union | Organize coordination meeting among health and family planning staff at UP Office. | UP Chairman | 210,000 | 230,000 | UP rep. union level health and FP staffs | Increase the coordination among them and people get quality service.  |
| 6 | Shortage of IFA in union level | -- | 4 unions | Supply chain have to maintain | UFPO | - | - | P. mother | IFA available all time in FWC, CC. |
| **Early Marriage (Child Marriage)** |
| 1 | Parents gave their daughter marriage before 18 yeas age due to poverty  | All union | All union | Awareness build-up of parents regarding bad impact of early marriage. Arrange safety net program for adolescent girls.  | CUP, Upazila and district administration, local elites | 4,500,000 | 4,800,000 | Adolescent girls | Reduce early marriage |
| 2 | Sometimes early marriage occurred due to evatising  | All union | All union | Social awareness raising against evatising | CUP, Upazila and district administration, local elites | 220,000 | 195,000 | Adolescent boys | Reduce evatising and early marriage |
| 3 | Dowry required less amount if daughter get married before 18  | All union | All union | Social protection raise-up against dowry | CUP, Upazila and district administration, local elites | 1,330,000 | 1,340,000 | Adolescent girls | Stopped dowry and reduce early marriage |
| **Child Labor** |
| 1 | Children engaged in labor for their parents long time illness | All union | All union | Awareness raising on bad effect of child labor. They can under safely net program like VGD, FGF, old allowance of their parents | CUP, Social service and women affairs department | 3,310,000 | 3,520,000 | Children age 14 years | Child labor will reduce |
| 2 | Sometimes Mussulmen engage children in labor and paid less amount  | All union | All union | Social protection raise against that Mussulmen those are engage children in job. | CUP, Social service and women affairs department | 300,000 | 250,000 | Children age 14 years | Child labor will reduce |
| 3 | There is no option of orphan children without sell labor | All union | All union | Orphan children have to go under safety net program.  | CUP, Social service and women affairs department | 2,530,000 | 2,840,000 | Orphan children | Child labor will reduce |
| **Recreation** |
| 1 | There is no recreation place in union level for the children. | 10 unions | 10 unions | Establishment of children knowledge and recreation Centre in union level | UP and local elites | 2,000,000 | 2,000,000 | Children,  | Child knowledge and recreation Centre establish at union level. |
| 2 | Less opportunity for children to play outdoor game.  | All union | All union | Develop school field for outdoor game, Find out khas land and occupied as playground.  | School teacher, UP and local elites | Budget included in education section | Budget included in education section | Children | Playground will develop. Children can get opportunity to play outdoor game |
| **Water and Sanitation** |
| 1 | In adequate number of safe drinking water points so that people collected water from long distance. | All union | All union | Need to install adequate number of safe drinking water points. Aware to people about benefit of safe drinking water  | DPHE, UP and NGOs | 16,500,000 | 7,070,000 | Community people | Adequate number of safe drinking water points installed and people collect water from that points  |
| 2 | Some people are not aware about the use of non-sanitary latrine  | All union | All union | Need to motivate people to use of sanitary latrine. Also aware them benefit of sanitary latrine use  | DPHE, UP and NGOs | 550,000 | 507,500 | Community people | Sanitary latrine user will be increased |
| 3 | Some people cannot install sanitary latrine due to poverty  | All union | All union | Achieve the 100% sanitation facility some cases subsidiary need to provide for the poor people.  | DPHE, UP and NGOs | 15,000,000 | 1,520,000 | Poor people | 100% achieve in sanitation facility.  |

Acronym –DCCC-District Convergence Coordination Committee, UzCCC- Upazila Convergence Coordination Committee, UCCC-Union Convergence Coordination Committee, WCCC-Ward Convergence Coordination Committee, CUP-Chairman of union parishad, MUP- Member of union parishad, SUP – Secretary of union parishad, UP – Union Parishad, LGI- Local Government Institute, DSS-Department of Social Service, DC-Deputy Commissioner, CS- Civil Surgeon, UH&FPO –Upazila Health and Family Planning Officer, HI – Health Inspector, AHI- Assistance Health Inspector, HA- Health Assistance, DD-FP-Deputy Director Family Planning, UFPO – upazila Family Planning Officer, FPI Family Planning Inspector, FWA Family well fair assistance, FP- Family Planning, DPHE-Department of Public Health Engineering, SAE Sub Assistance Engineer, XEN- Executive Engineer, UNO-Upazila Nirbahi Officer, DPEO – District Primary Education Officer, UEO – Upazila Education Office, AUEO – Assistance Upazila Education Officer, GPS- Government Primary School, BR- Birth Registration, SMC – School management committee. PPE- Pre Primary Education.

**Union Plan Compiled by: Approve by:**

**Abu Zafor Mohammad Asif Iqbal Nazmul Ahsan**

**District Child Affairs Officer, Bangladesh Shishu Academy, Satkhira and Deputy Commissioner, SAtkhira and**

**Member Secretary, District Convergence Coordination Committee – LCBCE, Project Chair Person, DCCC – LCBCE, Project**, **Satkhira**

**Technical supported by:**

 **Md. Aman Ullah**

 **Programme Officer (Planning and Monitoring), UNICEF, Khulna Field Office**