## Water Tech_details
Annual Hardware Progress Status
MIS Report
Promotion of Water Supply, Sanitation and Hygiene in Hard-to-Reach Areas of Rural Bangladesh
Name of PNGO & Address: PROTIVA, Rampal, Bagerhat
Period : December-11 from November-12
Water Technology Installation Status, Union: Perikhili, Upazila: Rampal, District: Bagerhat
SL. No. | Name of Technology | Technology code No. | Capacity (lit.) for RHWS, CBRWHS etc. | Caretaker's name |  | Ward No. | VDC No. | Village | No. of Benefitted H H | No. of Population |  |  | No. of women headed HH | No. of Hardcore Poor |  | Climate victims Peoples |  | No. Disable people |  | Financial Status |  | Installation Date (Day/Month Year) |  | Post Water Quality Test Information |  |  | Bore log data Depth (m) if applicable | Name of Contractor
|  |  |  | Male | Female |  |  |  |  | Male | Female | Total Population |  | Male | Female | Male | Female | Male | Female | Total Budget | Cost shared | Starting Date | Completion Date | TDS (mg/lit) | TC | FC
1 | RWHS | 10 | 3200 Ltr. | Saheb Ali | Anjira Begum | 4 | 7 | Singorbunia | 1 | 3 | 3 | 6 | 0 | 3 | 3 | 3 | 3 | 1 | 0 | 25000 | 2500 | 16.05.12 | 23.05.12 | 95 |  | 0 |  | Azibar Dhali
2 | RWHS | 10 | 3200 Ltr. | Selim Talukder | Zinufa Begum | 4 | 7 | Singorbunia | 2 | 6 | 4 | 10 | 1 | 6 | 4 | 6 | 4 | 0 | 0 | 25000 | 2500 | 16.05.12 | 23.05.12 | 47.3 |  | 0 |  | Azibar Dhali
3 | RWHS | 10 | 3200 Ltr. | Ibrahim | Jamila Begum | 5 | 9 | Romzaipur | 2 | 4 | 3 | 7 | 0 | 4 | 3 | 4 | 3 | 0 | 1 | 25000 | 2500 | 17.05.12 | 24.05.12 | 114.6 |  | 0 |  | Azibar Dhali
4 | RWHS | 10 | 3200 Ltr. | Aziz Mollah | Dolena Begum | 5 | 9 | Romzaipur | 1 | 3 | 3 | 6 | 0 | 3 | 3 | 3 | 3 | 1 | 0 | 25000 | 2500 | 17.05.12 | 24.05.12 | 35.3 |  | 0 |  | Azibar Dhali
5 | RWHS | 10 | 3200 Ltr. | Razib Adhikari | Pushpo Rani | 9 | 18 | Barokatali | 2 | 5 | 3 | 8 | 0 | 5 | 3 | 5 | 3 | 1 | 0 | 25000 | 2500 | 18.05.12 | 25.05.12 | 59.8 |  | 0 |  | Azibar Dhali
6 | RWHS | 10 | 3200 Ltr. | Bayezid Khan | Jochna Khatun | 9 | 18 | Barokatali | 1 | 4 | 3 | 7 | 1 | 4 | 3 | 4 | 3 | 0 | 1 | 25000 | 2500 | 18.05.12 | 25.05.12 | 55 |  | 0 |  | Azibar Dhali
7 | CBRWHS | 3 | 10000 Ltr. | Moloy Mondal | Ratna Rani Mondal | 4 | 8 | Singorbunia | 9 | 16 | 19 | 35 | 1 | 16 | 19 | 16 | 19 | 3 | 2 | 88000 | 8000 | 07.11.12 | 25.11.12 | 55.6 | 0 | 0 |  | Vobotosh Mondal
[9 empty] | 18 | 41 | 38 | 35 | 3 | 41 | 38 | 41 | 38 | 6 | 4 | 238000 | 23000 | [6 empty] | Ashok Mondal
This color marked Cell is Forumulated Cell, Please don’t change or delete
Note on B8: Tanvir: Follow the name of technologies - output serial number, then insert the technology name carefully
Note on A4: Type your Region Name

## Water Tech_HYSAWA (hidden)
Management Information System
Union wise Installation of Water Supply Technologies (Cumulative status)
Funded by - HYSAWA FMO
Sl. No. | Pump/ Plant Name | Depth (ft') | Capacity (Litter) | Caretaker name |  | No. of CDF /WWPC | Village | Union | Upazila | District | No of Benifited HH | Name of FNGO | Financial Status |  |  | Installation status |  | Installation period (Month / Year) | Water Quality tested ? | If Yes what is the Test result ? |  | Caretaker Training (Yes/No) | Provided Tools Manual (Yes/No)
|  |  |  | Male | Female | [7 empty] | Total Budget | 10% Cost shared | No. of Shared HH | Installation (Yes /No) | Platform (Yes/No) |  | Yes / No | Arsenic or TC | Iron or FC
1 | [13 empty] | 0
2 | [13 empty] | 0
3 | [13 empty] | 0
4 | [13 empty] | 0
5 | [13 empty] | 0
6 | [13 empty] | 0
7 | [13 empty] | 0
8 | [13 empty] | 0
9 | [13 empty] | 0
10 | [13 empty] | 0
11 | [13 empty] | 0
12 | [13 empty] | 0
13 | [13 empty] | 0
14 | [13 empty] | 0
15 | [13 empty] | 0
16 | [13 empty] | 0
17 | [13 empty] | 0
18 | [13 empty] | 0
19 | [13 empty] | 0
20 | [13 empty] | 0
Prpeared by : | [18 empty] | Checked by:
Designation: | [18 empty] | Designation:
Contact no: | [18 empty] | Contact no: